## completed-archive (hidden)
# | Complete | Date
2013
1 | Redesign: US Mobile
2 | Trendyr Reporting
3 | mPOS Redesign
4 | Redesign: PL/TW/US
5 | Japan Rollout | 2013-02-14
6 | eCom Mobility: Vendor Selection | 2013-02-13
7 | Skin/Code Updates to enable Adyen with Redesign
8 | Code Refactoring
9 | Adyen EU Rollout
10 | Kount Fraud CA
11 | CRM Customer Data
12 | Nordic Affiliate Tracking
13 | Redesign: AT | 2013-04-08
14 | Services Process Piloting
15 | Property Files Tool for BM
16 | Redesign: DE | DEV
17 | Dotomi First Party Cookie (6863)/Mobile Support (7352)
18 | Redesign: NL
19 | JP Transition: Criteo, MW Reporting | 2013-05-13
20 | Redesign: EU | 2013-05-13
21 | Redesign: UK | 2013-05-13
22 | Redesign: FI | 2013-05-13
23 | Mobility: mCommerce Proposal | 2013-05-13
24 | Free Shipping Test: Phase 1 | 2013-05-13
25 | Redesign: General | 2013-05-13
26 | Redesign: SE | 2013-05-13
27 | Mobility Roadmap | 2013-05-13
28 | Global Performance Dashboard - SOW 1 | 2013-05-13
29 | Redesign: ES | 2013-05-13
30 | Redesign: NO | 2013-05-13
31 | Redesign: FR | 2013-05-13
32 | Redesign: IT | 2013-05-13
33 | ForeSee SessionReplay Tracking
34 | Redesign: Customer Service Section Update
35 | Tag Management: Technical Implementation
36 | Redesign: AU
37 | Redesign: SG
38 | Redesign: HK
39 | JP Transition: ChannelAdvisor
40 | PayPal
41 | Site Optimization Code Review
42 | Adyen APAC
43 | Free Shipping Test: Phase 2 (Free Shipping Thresholds) | 2013-08-13
44 | Global Performance Dashboard - SOW 2 | 2013-08-13
45 | NPI: FH13 | 2013-08-13
46 | Omniture First Party Cookies | 2013-08-13
47 | AU Shipping Free Shipping Threshold Test | 2013-09-13
48 | Hi Conversion POC | 2013-09-13
49 | Redesign: JP/KR/BR Discovery | 2013-09-13
50 | Crocs club digital interface and data routing | 2013-10-01
51 | Free Shipping Test: Phase 3 | 2013-10-01
52 | Pod Move | 2013-10-01
53 | Improved RMA Messaging | 2013-10-01
54 | Adobe Media Optimizer
55 | Product Finder: Discovery
56 | Americas Assistance on Inventory
57 | BISN Triage Phase 1 (Backend)
58 | Redesign: JP/KR/BR General | 2013-10-01
59 | Stretch Sole Landing Page | 2013-11-01
60 | Mobile US Enhancement | 2013-11-01
61 | Recommendations in Transactional Emails (US) | 2013-11-01
62 | Tag Management: Marketing | 2013-11-01
63 | Tablet Optimization
| 2014 Roadmap | 12/2013

## release-pln-q1 (hidden)
Initiaive | Quarter | Quarter (static) | Status
2014 Roadmap | #REF! | Later | Active
Banner Optimization | Later | NA | Backlog
CrocsRx.ca | Later | NA | Backlog
Expanding Wish List Feature | Later | NA | Backlog
Free Offers | Later | NA | Backlog
Get US BazaarVoice Reviews into AU, SG | Later | NA | Backlog
Gift with purchase (GWP) | Later | NA | Backlog
Mobile Only Couponing | Later | NA | Backlog
NPI: Figs Scrubs | Later | NA | Backlog
PFD @ Work Loyalty Program | Later | NA | Backlog
Random Coupon Code Generator | Later | NA | Backlog
Seamless SMS-Opt-in Process Online | Later | NA | Backlog
Shipment Tracking number for AU/HK/SG/TW | Later | NA | Backlog
Adyen Rollout for AU | #REF! | Q1 | Active
Cart Level Upsell | #REF! | Q1 | Backlog
Checkout Redesign US | #REF! | Q1 | Backlog
CRM Data Capture EU/AP | #REF! | Q1 | Active
Dynamic Size Chips | #REF! | Q1 | Active
ExactTarget 2.0 | #REF! | Q1 | Active
JP Taxation Change | #REF! | Q1 | Active
Merchandising Automation, Phase 1 | #REF! | Q1 | Backlog
Mobile Site Global Rollout, Wave 2 | #REF! | Q1 | Backlog
Mobile Site Global Rollout, Wave 2 | #REF! | Q1 | Backlog
NPI: SS14 + Outsource | #REF! | Q1 | Active
ProductFinder | #REF! | Q1 | Active
Promotional Nearness Messaging | #REF! | Q1 | Backlog
SAP Card Connect Integration | Later | Q1 | Active
Site Performance Optimization | Later | Q1 | Active
Size Chart Rollout | Later | Q1 | Active
US ebay upgrades | Later | Q1 | Active
| #REF! | Q1 | Backlog
| #REF! | Q1 | Backlog
Crocs Club Rewards: eComm Integration and Customer Experience on Web | #REF! | Q2 | Active
Merchandising Automation, Phase 2 | #REF! | Q2 | Backlog
Mobile Site Global Rollout, Wave 1 | #REF! | Q2 | Active
Mobile Site Global Rollout, Wave 3 | #REF! | Q2 | Backlog
Redesign: BR | #REF! | Q2 | Active
Redesign: JP | #REF! | Q2 | Active
Redesign: KR | #REF! | Q2 | Active
SAP Implementation | #REF! | Q2 | Active
Adyen APAC, Phase 2 | #REF! | Q3 | Backlog
Demandware Transactional Email Redesign | #REF! | Q3 | Backlog
Product Sets | #REF! | Q3 | Backlog
Social Sign-In Enhancements | #REF! | Q3 | Backlog
Store Locator | #REF! | Q3 | Backlog
Storefront Toolkit | #REF! | Q3 | Backlog
TW/SG COD | #REF! | Q3 | Backlog

## priortization (hidden)
Backlog Projects | Conf Factor | FOM | GL eCom Team |  | Americas |  | EU |  | APAC |  | JP
|  |  | Effort | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Annual Cost Savings or Revenue Generation | Impact Value | Annual Cost Savings or Revenue Generation | Impact Value | Annual Cost Savings or Revenue Generation | Impact Value
NPI: Figs Scrubs | N¦N¦N¦Y | 4.25 | 1 week/only config change in 1 system | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
|  | 3.11 | 3 months/3 or less systems | 9 | CS: $1M+/R: $1.5M+ | 10 | CS: $1M+/R: $1.5M+ | 10 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $50K-75K/R: $75K-112.5K | 3
Mobile Site Global Rollout, Wave 1 | Y¦Y¦Y¦Y | 4.00 | 3 months+/4 + | 10 | CS: $1M+/R: $1.5M+ | 10 | CS: $1M+/R: $1.5M+ | 10 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $125K-200K/R: $187.5K-300K | 5
BISN Triage Phase 1 (Backend) | N¦N¦N¦N | 2.80 | 1 month/3 or less systems | 5 | CS: $200K-300K/R: $300K-450K | 6 | CS: $200K-300K/R: $300K-450K | 6 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Product Sets | Y¦N¦N¦N | 2.69 | 3 months/3 or less systems | 9 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $200K-300K/R: $300K-450K | 6 | CS: $50K-75K/R: $75K-112.5K | 6 | CS: $50K-75K/R: $75K-112.5K | 6
PayPal SG | Y¦Y¦Y¦Y | 2.00 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1
Gift with purchase (GWP) | Y¦N¦N¦Y | 2.38 | 2 months/4 + | 8 | CS: $200K-300K/R: $300K-450K | 6 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 3 | CS: $0-25K/R: $0-37.5K | 3
Google Trusted Store | N¦N¦N¦N | 1.57 | 2 months/3 or less systems | 7 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Mobile Only Couponing | N¦N¦N¦N | 1.80 | 1 month/3 or less systems | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
US ebay upgrades | Y¦Y¦Y¦Y | 2.14 | 2 months/3 or less systems | 7 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
ShoeFinder | Y¦N¦Y¦Y | 3.18 | 2 months/3 or less systems | 7 | CS: $500K-750K/R: $750K-1.125M | 8 | CS: $300K-500K/R: $450K-750K | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Akamai EU | Y¦N¦Y¦Y | 3.00 | 3 weeks/contained in 1 system | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $200K-300K/R: $300K-450K | 6 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
CRM Data Capture EU/AP | N¦Y¦Y¦Y | 2.08 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $200K-300K/R: $300K-450K | 6 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1
CrocsRx.ca | Y¦N¦N¦N | 1.45 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
KR Virtual Account Bank Transfer Adyen-Inicis | N¦N¦N¦Y | 2.13 | 2 months/4 + | 8 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 8 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $0-25K/R: $0-37.5K | 1
Expanding Wish List Feature | N¦N¦N¦N | 1.29 | 2 months/3 or less systems | 7 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Americas Phase 1 Crocs Club Rewards: eComm Integration and Customer Experience on Web | N¦N¦N¦N | 1.13 | 2 months/4 + | 8 | CS: $200K-300K/R: $300K-450K | 6 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Random Coupon Code Generator | N¦N¦N¦N | 0.80 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Shipment Tracking number for AU/HK/SG/TW | N¦N¦N¦N | 0.86 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2
TW/SG COD | N¦N¦N¦N | 1.20 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1
Free Offers | N¦N¦N¦N | 0.70 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2
Checkout Redesign US | Y¦N¦Y¦Y | 2.64 | 3 months/3 or less systems | 9 | CS: $1M+/R: $1.5M+ | 10 | CS: $0-25K/R: $0-37.5K | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Merchandising Automation, Phase 1 | N¦Y¦Y¦Y | 1.53 | 3 months/3 or less systems | 9 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Storefront Toolkit | Y¦Y¦N¦Y | 1.75 | 1 month/3 or less systems | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Cart Improvements, Phase 3: Promotional Nearness Messaging | N¦Y¦N¦Y | 2.36 | 2 months/3 or less systems | 7 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1 | CS: $125K-200K/R: $187.5K-300K | 5
PFD @ Work Loyalty Program | N¦N¦N¦N | 0.40 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Merchandising Automation, Phase 2 | N¦Y¦Y¦Y | 1.53 | 3 months/3 or less systems | 9 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Social Sign-In Enhancements | Y¦N¦Y¦Y | 1.95 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Active Projects
Tag Management |  | 4.00 | 3 weeks/contained in 1 system | 2 | CS: $200K-300K/R: $300K-450K | 4 | CS: $50K-75K/R: $75K-112.5K | 2 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Site Performance Optimization | Y¦Y¦Y¦Y | 4.90 | 3 months+/4 + | 10 | CS: $1M+/R: $1.5M+ | 10 | CS: $1M+/R: $1.5M+ | 10 | CS: $750K-1M/R: $1.125M-1.5M | 9 | CS: $1M+/R: $1.5M+ | 10
Redesign: BR | Y¦Y¦Y¦Y | 1.67 | 3 months/3 or less systems | 9 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Cart Improvements, Phase 2: Cart Level Upsell | Y¦N¦Y¦N | 1.64 | 2 months/3 or less systems | 7 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2
Redesign: JP | Y¦Y¦Y¦Y | 1.89 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $125K-200K/R: $187.5K-300K | 5
Demandware Transactional Email Redesign | Y¦Y¦Y¦Y | 2.71 | 2 months/3 or less systems | 7 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $50K-75K/R: $75K-112.5K | 3
Tablet Optimization | Y¦Y¦N¦Y | 3.75 | 1 month/3 or less systems | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $200K-300K/R: $300K-450K | 6 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1
JP Taxation Change | N¦N¦N¦Y | 1.05 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $125K-200K/R: $187.5K-300K | 5
Dynamic Size Chips | N¦N¦N¦Y | 1.05 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
SAP Card Connect Integration | N¦N¦Y¦Y | 1.80 | 3 months+/4 + | 10 | CS: $1M+/R: $1.5M+ | 10 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Banner Optimization | Y¦N¦N¦Y | 3.10 | 1 month/3 or less systems | 5 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $50K-75K/R: $75K-112.5K | 3
LinkShare: Automated Reconciliation | Y¦N¦N¦Y | 2.50 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $200K-300K/R: $300K-450K | 6 | CS: $1M+/R: $1.5M+ | 10 | CS: $0-25K/R: $0-37.5K | 1
Adyen Rollout for AU | Y¦N¦Y¦Y | 2.61 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $1M+/R: $1.5M+ | 10 | CS: $0-25K/R: $0-37.5K | 1
Get US BazaarVoice Reviews into AU, SG | Y¦N¦N¦Y | 1.17 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1
Mobile Site Global Rollout, Wave 2 | Y¦Y¦N¦Y | 1.55 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Cart Improvements | Y¦Y¦Y¦Y | 4.14 | 2 months/3 or less systems | 7 | CS: $500K-750K/R: $750K-1.125M | 8 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $125K-200K/R: $187.5K-300K | 5
Checkout Redesign International | Y¦Y¦N¦Y | 3.04 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $200K-300K/R: $300K-450K | 6 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $200K-300K/R: $300K-450K | 6
Redesign: KR | Y¦Y¦Y¦Y | 1.78 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1
Improved newsletter registration workflow APAC | Y¦Y¦Y¦Y | 1.86 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1
CDN Optimization | Y¦N¦Y¦Y | 1.75 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1
SEO Url Optimization | Y¦N¦Y¦Y | 2.75 | 3 months+/4 + | 10 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $125K-200K/R: $187.5K-300K | 5
Global PDP Enhancements, Phase 2 | N¦N¦N¦Y | 1.69 | 3 months/3 or less systems | 9 | CS: $200K-300K/R: $300K-450K | 6 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2
Global PDP Enhancements, Phase 1 | N¦N¦N¦Y | 1.14 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $50K-75K/R: $75K-112.5K | 3
Translation Tools | Y¦N¦Y¦Y | 1.97 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $300K-500K/R: $450K-750K | 7 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1
PayPal AU | Y¦Y¦Y¦Y | 2.80 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $200K-300K/R: $300K-450K | 6 | CS: $0-25K/R: $0-37.5K | 1
Adyen TW | Y¦Y¦Y¦Y | 1.57 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Mobile Site Global Rollout, Wave 4 | Y¦Y¦N¦Y | 1.55 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Localize Merchandise Automation Reports | Y¦Y¦Y¦Y | 1.44 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Sears Marketplace | N¦N¦Y¦Y | 1.17 | 3 months/3 or less systems | 9 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
SheerID Military ID Check | Y¦Y¦Y¦Y | 2.00 | 3 months/3 or less systems | 9 | CS: $200K-300K/R: $300K-450K | 6 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Localize Shoefinder | Y¦Y¦Y¦Y | 1.44 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Card Connect, 1-Step Refactor | Y¦Y¦Y¦Y | 1.67 | 1 month/4 + | 6 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
New Projects
Smartphone Geo-targeted home page targeted at retail | Y¦N¦Y¦Y | 2.04 | 2 months/3 or less systems | 7 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2
Call Center App | Y¦N¦Y¦Y | 1.86 | 3 months/3 or less systems | 9 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Copy this Row |  | 0.44 | 3 months/3 or less systems | 9 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Completed/Archived Projects
PayPal |  | 4.33 | 2 weeks/contained in 1 system | 3 | CS: $1M+/R: $1.5M+ | 10 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Crocs club digital interface and data routing |  | 3.11 | 3 months/3 or less systems | 9 | CS: $300K-500K/R: $450K-750K | 7 | CS: $300K-500K/R: $450K-750K | 7 | CS: $300K-500K/R: $450K-750K | 7 | CS: $300K-500K/R: $450K-750K | 7
NPI Translation Workflow Tool |  | 0.78 | 3 months/3 or less systems | 9 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Product Feed Fixes/Improvements to optimize Comparison Shopping Engines) |  | 3.67 | 2 weeks/contained in 1 system | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2
Couponing/Promo code redesign |  | 3.40 | 1 month/3 or less systems | 5 | CS: $300K-500K/R: $450K-750K | 7 | CS: $300K-500K/R: $450K-750K | 7 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $50K-75K/R: $75K-112.5K | 3
Channel Advisor CSE Categorization | Y¦N¦N¦Y | 1.39 | 3 months/3 or less systems | 9 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Improved Online Coupon Messaging |  | 2.20 | 1 month/3 or less systems | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $50K-75K/R: $75K-112.5K | 3 | CS: $50K-75K/R: $75K-112.5K | 3
Discount pricing by percentage in category and other |  | 2.00 | 3 weeks/contained in 1 system | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $25K-50K/R: $37.5K-75K | 3 | CS: $25K-50K/R: $37.5K-75K | 3
Account Form Update |  | 1.50 | 3 weeks/contained in 1 system | 4 | CS: $75K-125K/R: $112.5K-187.5K | 4 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Loyalty/CRM Retail Sign-Up via iPad |  | 1.29 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $300K-500K/R: $450K-750K | 7 | CS: $300K-500K/R: $450K-750K | 7
Catalog Sign-Up and Removal Form on Customer Service Page |  | 1.00 | 1 month/3 or less systems | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Baltics Rollout |  | 0.70 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | CS: $125K-200K/R: $187.5K-300K | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Gift Card Bug Fix |  | 0.43 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Kount (fraud management) in APAC |  | 0.43 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Seamless SMS-Opt-in Process Online |  | 0.60 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Improved Filters |  | 0.60 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Field Change Request for Email Sign-up Page (APAC) |  | 1.20 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | CS: $25K-50K/R: $37.5K-75K | 2
Improved RMA Messaging |  | 2.00 | 2 weeks/contained in 1 system | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 3 | CS: $0-25K/R: $0-37.5K | 1 | CS: $0-25K/R: $0-37.5K | 1
Note on D1: Is there third party research available to support this? Is there pilot data (i.e. Project exists in another region)? Are there historical metrics (i.e. Similar projects with other companies)? Is the likelihood high that the user will adopt the functionality?

## priortization v2 (hidden)
Projects |  | Region | Date Added | Date Needed | FOM | eCom Team |  | Americas |  |  |  | EU |  |  |  | APAC
| Note |  |  |  |  | Effort | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Cost/Effort to Implement | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Cost/Effort to Implement | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Cost/Effort to Implement | Difficulty Value
Couponing/Promo code redesign |  | Global | 2012-01-04 | 2012-06-30 | 1.42 | 1 month/3 or less systems | 5 | CS: $300K-500K/R: $450K-750K | 7 | C: $25K-50K/E: 2 weeks | 2 | CS: $300K-500K/R: $450K-750K | 7 | C: $25K-50K/E: 2 weeks | 2 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $50K-75K/E: 3 weeks | 3
Improved Online Coupon Messaging |  |  |  |  | 1.38 | 1 month/3 or less systems | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $0-25K/E: 1 week | 1 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $0-25K/E: 1 week | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $0-25K/E: 1 week | 1
Recommendation engine |  | Global | 2012-01-10 | 2012-06-30 | 1.36 | 2 months/3 or less systems | 7 | CS: $750K-1M/R: $1.125M-1.5M | 9 | C: $50K-75K/E: 3 weeks | 3 | CS: $300K-500K/R: $450K-750K | 7 | C: $50K-75K/E: 3 weeks | 3 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $0-25K/E: 1 week | 1
Google Trusted Store |  |  |  |  | 1.25 | 2 weeks/contained in 1 system | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $50K-75K/E: 3 weeks | 3 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Gift with purchase (GWP) |  | Global | 2011-09-12 | 2012-03-31 | 1.20 | 3 weeks/contained in 1 system | 4 | CS: $200K-300K/R: $300K-450K | 6 | C: $25K-50K/E: 2 weeks | 2 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 3 | C: $25K-50K/E: 2 weeks | 2
BISN Triage Phase 1 (Backend) |  | Global | 2011-05-18 | 2011-09-30 | 1.08 | 3 weeks/contained in 1 system | 4 | CS: $200K-300K/R: $300K-450K | 6 | C: $50K-75K/E: 3 weeks | 3 | CS: $200K-300K/R: $300K-450K | 6 | C: $50K-75K/E: 3 weeks | 3 | CS: $0-25K/R: $0-37.5K | 1 | C: $25K-50K/E: 2 weeks | 2
Product Sets |  | Global | 2011-05-11 | 2011-09-30 | 1.07 | 1 month/3 or less systems | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $50K-75K/E: 3 weeks | 3 | CS: $200K-300K/R: $300K-450K | 6 | C: $75K-125K/E: 4 weeks | 4 | CS: $50K-75K/R: $75K-112.5K | 6 | C: $50K-75K/E: 3 weeks | 3
Product Feed Fixes/Improvements to optimize Comparison Shopping Engines) |  | Global | 2011-05-13 |  | 1.00 | 2 weeks/contained in 1 system | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $25K-50K/E: 2 weeks | 2 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $25K-50K/E: 2 weeks | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $75K-125K/E: 4 weeks | 4
Self-Service Cancellation of orders |  |  |  |  | 1.00 | 2 months/3 or less systems | 7 | CS: $1M+/R: $1.5M+ | 10 | C: $50K-75K/E: 3 weeks | 3 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $25K-50K/E: 2 weeks | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $25K-50K/E: 2 weeks | 2
Discount pricing by percentage in category and other |  | Global | 2011-10-24 | 2012-06-30 | 0.89 | 3 weeks/contained in 1 system | 4 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $25K-50K/E: 2 weeks | 2 | CS: $25K-50K/R: $37.5K-75K | 3 | C: $25K-50K/E: 2 weeks | 2
Account Form Update |  |  |  |  | 0.86 | 3 weeks/contained in 1 system | 4 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Catalog Sign-Up and Removal Form on Customer Service Page | Pinged Andrea; already live | Americas | 2011-11-15 | 2012-02-14 | 0.71 | 1 month/3 or less systems | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week |  | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Field Change Request for Email Sign-up Page (APAC) |  |  |  |  | 0.50 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week | 1
Improved RMA Messaging |  |  |  |  | 0.50 | 2 weeks/contained in 1 system | 3 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Mobile Only Couponing |  |  |  |  | 0.50 | 1 month/3 or less systems | 5 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $50K-75K/E: 3 weeks | 3 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $125K-200K/E: 5 weeks | 5
Baltics Rollout |  |  |  |  | 0.50 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Seamless SMS-Opt-in Process Online |  | Americas | 2011-10-14 | 2012-03-30 | 0.38 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Improved Filters |  |  |  |  | 0.38 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Free Offers |  |  |  |  | 0.36 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | C: $25K-50K/E: 2 weeks | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week | 1
PFD @ Work Loyalty Program |  |  |  |  | 0.21 | 3 months+/4 + | 10 | CS: $0-25K/R: $0-37.5K | 1 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Gift Card Bug Fix |  | Global | 2012-01-15 | 2012-05-01 | 0.20 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | C: $50K-75K/E: 3 weeks | 3 | CS: $0-25K/R: $0-37.5K | 1 | C: $50K-75K/E: 3 weeks | 3 | CS: $0-25K/R: $0-37.5K | 1 | C: $25K-50K/E: 2 weeks | 2
PayPal |  |  |  |  | 2.00 | 2 weeks/contained in 1 system | 3 | CS: $1M+/R: $1.5M+ | 10 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Mobile Site Global Rollout |  |  |  |  | 1.47 | 3 months+/4 + | 10 | CS: $1M+/R: $1.5M+ | 10 | C: $0-25K/E: 1 week | 1 | CS: $1M+/R: $1.5M+ | 10 | C: $50K-75K/E: 3 weeks | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $50K-75K/E: 3 weeks | 3
CrocsRx.ca |  |  |  |  | 0.63 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
New Projects (need Impact/Difficulty from each Region)
Kount (fraud management) in APAC |  |  |  |  | 0.30 | 2 months/3 or less systems | 7 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Expanding Wish List Feature |  |  |  |  | #N/A |  | #N/A | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
(Blank Row to Copy¦Paste) |  |  |  |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A

## allocation-original (hidden)
week of
Resource | Project | % Allocation | 2012-08-03 | 8/10 | 8/17 | 8/24 | 8/31 | 9/7 | 9/14 | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30
CMcGinnie | Bugs/Maintenance | 40 | bar: week of 2012-08-03 to week of 11/9
| Site Redesign | 40 | bar: week of 2012-08-03 to week of 9/21
| Japan Rollout - Size Chips | 20 | bar: week of 8/24 to week of 9/7
AJuretus | Bugs/Maintenance | 10 | bar: week of 2012-08-03 to week of 11/9
| Japan Rollout - Mobile | 60 | bar: week of 2012-08-03 to week of 10/26
| ForeSee | 30 | bar: week of 8/31 to week of 10/5
ZSeeling | Bugs/Maintenance | 45 | bar: week of 2012-08-03 to week of 11/9
| Japan Rollout - Skins / Styling | 45 | bar: week of 8/17 to week of 10/26
| Adyen EU Rollout | 10
JLong | Bugs/Maintenance | 20 | bar: week of 2012-08-03 to week of 11/9
| Japan Rollout - MW | 30 | bar: week of 8/31 to week of 9/28
| CRM Phase 2 | 30 | bar: week of 2012-08-03 to week of 11/9
| mPOS | 20 | bar: week of 8/10 to week of 8/31
SDeitz | Bugs/Maintenance | 20 | bar: week of 2012-08-03 to week of 11/9
| Japan Rollout - Data loading | 40 | bar: week of 8/17 to week of 10/19
| Ops | 30 | bar: week of 2012-08-03 to week of 11/9
PMcElroy | Bugs/Maintenance | 10 | bar: week of 2012-08-03 to week of 11/9
| Brazil Rollout - Ops | 20 | bar: week of 2012-08-03 to week of 8/31
| Japan Rollout - dev MGT | 25 | bar: week of 2012-08-03 to week of 10/26
| Site Redesign - dev MGT | 20 | bar: week of 2012-08-03 to week of 10/26
| CRM Phase 2 - dev MGT | 15 | bar: week of 2012-08-03 to week of 9/14
| mPOS - dev / dev MGT | 10 | bar: week of 2012-08-03 to week of 8/31
Nkuhnel | Bugs/Maintenance | 20 | bar: week of 2012-08-03 to week of 11/9
| Certona | 20 | bar: week of 2012-08-03 to week of 9/21
| Japan Rollout | 20 | bar: week of 2012-08-03 to week of 11/9
| Mentoring | 20 | bar: week of 2012-08-03 to week of 11/9
| VML | 20 | bar: week of 2012-08-03 to week of 10/26
Offshore team | Bugs/Maintenance | 10 | bar: week of 2012-08-03 to week of 11/9
| Japan Rollout | 60 | bar: week of 2012-08-03 to week of 10/26
| Vacation | 5 | bar: week of 2012-08-03 to week of 8/31
| Regression Testing | 25 | bar: week of 2012-08-03 to week of 11/9

## archive-wk-15 (hidden)
Team | Resource | Project | Activity | 2012-01-07 | 1/14 | 1/21 | 1/28 | 2/4 | 2/11 | 2/18 | 2/25 | 3/3 | 3/10 | 3/17 | 3/24 | 3/31 | 4/7 | 4/14 | 4/21 | 4/28 | 5/5 | 5/12 | 5/19 | 5/26 | 6/2 | 6/9
dev | CMcGinnie | Redesign: General | Bug Fixes, Mega Menus | 16 | 16 | 16 | 16 | 16 | 28 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
dev | CMcGinnie | Bugs/Maintenance | Misc. | 10 | 10 | 12 | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | CMcGinnie | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | CMcGinnie | PayPal | Kick off / review |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | CMcGinnie | TOTAL Avail: CMcGinnie |  | 26 | 26 | 42 | 42 | 42 | 46 | 46 | 32 | 46 | 46 | 46 | 46 | 32 | 46 | 42 | -32 | -32 | -32 | -12 | 0 | -7 | 0 | 0
dev | AJuretus | Bugs/Maintenance | Misc. | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 12 | 12 | 15 | 30 | 30 | 30 | 30 | 30 | 30 | 30
dev | AJuretus | JP Transition | Misc. | 6 | 6 | 6 | 6 | 6 | 17 | 8 | 6 | 12 | 6 | 6 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | AJuretus | Redesign: Customer Service Section Update | Misc. | 2 | 2 | 18 | 8 | 8 | 15 | 16 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | AJuretus | ForeSee SessionReplay Tracking | Dev | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | AJuretus | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | AJuretus | TOTAL Avail: AJuretus |  | 24 | 24 | 34 | 22 | 22 | 32 | 32 | 32 | 38 | 32 | 32 | 32 | 32 | 32 | 32 | 25 | 2 | 2 | 2 | 2 | -5 | 2 | 2
dev | JLong | Code Refactoring | EDW/MW | 16 | 16 | 16 | 16 | 16 | 4 | 16 | 16 | 16 | 12 | 16 | 4 | 4 | 4 | 10 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
dev | JLong | EU RMA | MW | [15 empty] | 6 | 4 | 6 | 4 | 4 | 4 | 4 | 4
dev | JLong | JP Transition | Middleware | 4 | 4 | 4 | 4 | 4 | 16 | 4 | 4 | 4 | 10 | 4 | 16 | 16 | 16 | 16 | 10 | 12 | 10 | 2 | 0 | 0 | 0 | 0
dev | JLong | CRM Customer Data | Phase 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
dev | JLong | PayPal | QA S1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 2 | 15 | 15 | 5 | 5 | 5
dev | JLong | SAP Meetings | B2C | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 10 | 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
dev | JLong | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | JLong | TOTAL Avail: JLong |  | 34 | 34 | 34 | 34 | 34 | 30 | 30 | 30 | 30 | 32 | 30 | 30 | 32 | 30 | 32 | -2 | -2 | -2 | -5 | -3 | 0 | 7 | 7
dev | SDeitz | Bugs/Maintenance | Misc. | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
dev | SDeitz | NPI: FH13 | Train Resource/processing | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 6 | 6 | 6 | 10 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0
| SDeitz | EU RMA / WM testing | DW / MW | [15 empty] | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6
dev | SDeitz | Akamai EU | EU/FR/FI | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4
dev | SDeitz | JP Transition | Data Loading | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
dev | SDeitz | Ops | Misc. | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
dev | SDeitz | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | SDeitz | TOTAL Avail: SDeitz |  | 48 | 38 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 34 | 36 | 32 | 36 | 32 | -4 | -4 | -4 | -5 | -4 | -11 | -4 | -4
dev | NKuhnel | Bugs/Maintenance | Misc. | 16 | 16 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15
dev | NKuhnel | Team Management | Mentoring | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
dev | NKuhnel | PayPal | tech spec for DW link cartridge/dev | 8 | 8 | 10 | 10 | 10 | 28 | 28 | 28 | 28 | 23 | 28 | 23 | 23 | 23 | 21 | 12 | 2 | 10 | 16 | 16 | 16 | 16 | 16
dev | NKuhnel | Adyen APAC | HK | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 5 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
dev | NKuhnel | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | NKuhnel | TOTAL Avail: NKuhnel |  | 30 | 30 | 26 | 26 | 26 | 32 | 32 | 32 | 32 | 27 | 32 | 32 | 29 | 32 | 32 | 14 | 24 | 16 | -5 | -5 | -12 | -5 | -5
dev | Offshore team | Bugs/Maintenance |  | 10 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 118 | 118 | 90 | 118 | 80 | 80 | 80 | 80
dev | Offshore team | Regression Testing | Automation | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 72 | 72 | 0 | 72 | 20 | 20 | 20 | 20
dev | Offshore team | PayPal | Development | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 2 | 20 | 80 | 80 | 80 | 80 | 80
dev | Offshore team | Redesign: General |  | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 14 | 14 | 14 | 110 | 118 | 90 | 118 | 0 | 0 | 0 | 0
dev | Offshore team | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | Offshore team | TOTAL Avail: Offshore team |  | 26 | 26 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 34 | 34 | 34 | 10 | 10 | 120 | -68 | 140 | 133 | 140 | 140
dev | PMcElroy | Bugs/Maintenance |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 16 | 6 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | PMcElroy | JP Transition | dev Mangagement | 8 | 8 | 12 | 12 | 12 | 12 | 16 | 0 | 12 | 12 | 12 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | PMcElroy | Demandware Outreach/Regional Site Manager Support | Burning the midnight tequila. | [11 empty] | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | PMcElroy | CRM Customer Data | Getting the systems set up | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | PMcElroy | PayPal | QA S1 | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2
dev | PMcElroy | Kount Fraud CA |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | PMcElroy | Redesign: NO | golive | [19 empty] | 1 | 0 | 0 | 0
dev | PMcElroy | Redesign: ES | golive | [19 empty] | 1 | 0 | 0 | 0
dev | PMcElroy | Redeisgn: IT | staging | [19 empty] | 3 | 0 | 0 | 0
dev | PMcElroy | Redeisgn: IT | golive | [19 empty] | 0 | 1 | 0 | 0
dev | PMcElroy | CRM Data into Salesforce | Meeting w/APAC | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dev | PMcElroy | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
dev | PMcElroy | TOTAL Avail: PMcElroy |  | 41 | 52 | 54 | 54 | 54 | 59 | 62 | 10 | 40 | 40 | 45 | 42 | 42 | 37 | 29 | 32 | 32 | 32 | 32 | 25 | 22 | 30 | 30
ops | KBaltus | Redesign: NO |  | 10 | 14 | 8 | 2 | 2 | 22 | 22 | 0 | 28 | 20 | 24 | 24 | 24 | 24 | 4 | 4 | 8 | 4 | 2 | 3 | 0 | 0 | 0
ops | KBaltus | Redesign: ES |  | 10 | 14 | 8 | 2 | 2 | 22 | 22 | 0 | 28 | 20 | 24 | 24 | 24 | 24 | 4 | 4 | 8 | 4 | 2 | 3 | 0 | 0 | 0
ops | KBaltus | Mobility: mCommerce Discovery | [10 empty] | 20 | 16 | 0 | 10 | 10 | 10 | 10 | 5 | 2 | 10 | 10 | 10 | 10 | 0
ops | KBaltus | Team Management | Bug Triage | 10 | 20 | 20 | 20 | 20 | 8 | 8 | 0 | 0 | 0 | 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
ops | KBaltus | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 7 | 7 | 0 | 0
ops | KBaltus | TOTAL Avail: KBaltus |  | 30 | 48 | 36 | 24 | 24 | 52 | 52 | 0 | 56 | 60 | 66 | 58 | 68 | 68 | 28 | 4 | 1 | 12 | 8 | -1 | 5 | 12 | 22
ops | JComstock | NPI | Bugs | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ops | JComstock | TOTAL Avail: JComstock |  | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ops | DWiliams | NPI: FH13 | Getting items in DW | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 15 | 0 | 20 | 20 | 10 | 10
ops | DWiliams | NPI | Bugs | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 10 | 10 | 5 | 5
ops | DWiliams | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 0 | 0 | 0
ops | DWiliams | TOTAL Avail: DWiliams |  | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -15 | 0 | 0 | -15 | -15 | 0 | 0
ops | JZapin | Team Management | Program Mgmt | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2
ops | JZapin | PayPal | QA S1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 15 | 15 | 10 | 10 | 10
ops | JZapin | eCom CFT | Getting the systems set up | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5
ops | JZapin | NPI: FH13 | Insuring products are entered | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 2 | 2 | 2 | 2 | 2
ops | JZapin | Mobility Roadmap |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 6 | 3 | 3 | 3 | 0 | 0
ops | JZapin | Mobile Site Global Rollout |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 6 | 3 | 3 | 3 | 3 | 3
ops | JZapin | Redesign: General |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 5 | 1 | 1 | 1 | 1
ops | JZapin | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 7 | 7 | 0 | 0
ops | JZapin | TOTAL Avail: JZapin |  | 47 | 47 | 47 | 47 | 47 | 57 | 57 | 57 | 57 | 53 | 53 | 48 | 53 | 53 | 53 | -21 | -2 | -8 | -3 | -6 | -1 | 9 | 9
svc | RBell | Global Performance Dashboard - SOW 1 | [18 empty] | 5 | 0 | 0 | 0 | 0 | 0
svc | RBell | Global Performance Dashboard - SOW 2 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 5 | 0 | 10 | 5 | 5 | 5 | 10 | 0 | 0 | 10 | 10
svc | RBell | Team Management |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5 | 5 | 10 | 10 | 5 | 5 | 10 | 5 | 0 | 0 | 10 | 10
svc | RBell | PPC Analysis/Recommendations | [16 empty] | 2 | 6 | 10 | 5 | 0 | 0 | 0 | 0
svc | RBell | JP Transition: ChannelAdvisor, Criteo, MW Reporting | [18 empty] | 5 | 2 | 0 | 0 | 0 | 0
svc | RBell | Site Optimization Code Review | [18 empty] | 2 | 2 | 0 | 0 | 0 | 0
svc | RBell | Tag Management: Marketing | [18 empty] | 5 | 3 | 0 | 0 | 10 | 10
svc | RBell | Various e-marketing data / report extracts | [13 empty] | 5 | 20 | 10 | 20 | 20 | 0 | 5 |  |  | 2 | 2
svc | RBell | OoO | [20 empty] | 32 | 32 | 0 | 0
svc | RBell | TOTAL Avail: RBell |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 15 | 15 | 10 | 30 | 0 | -4 | -10 | 0 | 0 | 0 | 0 | 0
svc | WChambers | Team Management | Training + Status | [17 empty] | 5 | 5 | 10 | 10 | 5 | 5
svc | WChambers | Global Performance Dashboard - SOW 2 | [18 empty] | 0 | 0 | 5 | 5 | 5 | 5
svc | WChambers | Tag Management: Marketing | [18 empty] | 0 | 0 | 5 | 5 | 5 | 5
svc | WChambers | PPC Analysis/Recommendations |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 20 | 10 | 5 | 10 | 10 | 15 | 15 | 15 | 15 | 10 | 10 | 5 | 5 | 5 | 5
svc | WChambers | Various e-marketing data / report extracts |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 15 | 20 | 30 | 25 | 20 | 15 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 10
svc | WChambers | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
svc | WChambers | TOTAL Avail: WChambers |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 35 | 30 | 35 | 35 | 30 | 30 | 35 | 2 | 2 | 2 | 2 | -8 | -15 | 2 | 2
svc | HNemann | PayPal |  | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2
svc | HNemann | Redesign: General | RMA Pages/TW Checklist | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 11 | 6 | 6 | 6 | 6 | 6
svc | HNemann | Redesign: General | Shopping Cart |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
svc | HNemann | Redesign: General | User Testing | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 11 | 11 | 6 | 6 | 6
svc | HNemann | Customer Service weekly CFT meeting | Quarterly CSR Outreach | [15 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
svc | HNemann | Free Shipping Test | Optimization Tests | [11 empty] | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 9 | 9 | 4 | 4 | 4
svc | HNemann | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
svc | HNemann | TOTAL Avail: HNemann |  | 20 | 15 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 30 | 30 | 30 | 34 | 0 | 0 | -3 | 2 | 2 | 5 | 12 | 12
svc | MSampson | JP Transition |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
svc | MSampson | Email Marketing |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
svc | MSampson | QA Builds/Projects | UAT/Build testing | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 15 | 20 | 10 | 20 | 25 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
svc | MSampson | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
svc | MSampson | TOTAL Avail: MSampson |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 25 | 25 | 25 | 30 | 30 | 25 | 25 | 7 | 7 | 7 | 7 | 7 | 0 | 7 | 7
svc | JGeditz | JP Transition |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 6 | 5 | 2 | 5 | 1 | 2 | 2 | 2 | 2 | 2 | 2
svc | JGeditz | Automated Regression |  | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 1 | 2 | 2 | 2 | 5 | 5 | 10 | 4 | 2 | 2 | 2 | 2 | 2
svc | JGeditz | PayPal | QA Plan. JG: Put in the time you think here | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 1 | 2 | 2 | 2 | 5 | 5 | 10 | 8 | 20 | 10 | 10 | 10 | 10
svc | JGeditz | QA Builds/Projects |  |  |  | 2 | 10 | 2 | 2 | 2 | 10 | 25 | 25 | 24 | 25 | 25 | 25 | 25 | 20 | 25 | 20 | 15 | 20 | 20 | 20 | 20
svc | JGeditz | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
svc | JGeditz | TOTAL Avail: JGeditz |  | 20 | 20 | 32 | 20 | 32 | 32 | 32 | 40 | 35 | 35 | 36 | 35 | 35 | 34 | 37 | -3 | -14 | -2 | -7 | -2 | -9 | -2 | -2
svc | MFrance | NPI | Bug Support | [11 empty] | 10 | 5 | 5 | 10 | 8 | 10 | 5 | 7 | 5 | 5 | 5 | 5
svc | MFrance | Team Management | Coord. Training | [17 empty] | 0 | 0 | 10 | 10 | 5 | 5
svc | MFrance | Demandware Outreach/Regional Site Manager Support |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 |  | 10 | 5 | 10 | 20 | 20 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
svc | MFrance | Bugs/Maintenance |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 10 | 10 | 15 | 5 | 5 | 10 | 5 | 5 | 8 | 5 | 5 | 5 | 5 | 5
svc | MFrance | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
svc | MFrance | TOTAL Avail: MFrance |  | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 5 | 20 | 15 | 35 | 30 | 30 | 35 | -1 | -3 | -1 | 0 | -8 | -15 | -3 | -3
svc | BHemphill | PayPal | Func Spec revision/team guidance | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 2 | 4 | 2 | 2 | 2 | 2 | 2 | 2
svc | BHemphill | Mobility: mCommerce Discovery |  | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 4 | 2 | 4 | 2
svc | BHemphill | Team Management | Coord. Training | [17 empty] | 0 | 0 | 5 | 5 | 5 | 5
svc | BHemphill | Adyen APAC |  | 10 |  | 20 | [9 empty] | 5 |  |  | 4 | 8 | 4 | 8 | 8 | 8 | 8 | 8
svc | BHemphill | Various e-marketing data / report extracts | [16 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
svc | BHemphill | Demandware Outreach/Regional Site Manager Support |  | 10 |  | 20 | [9 empty] | 21 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
svc | BHemphill | OoO |  | 8 | 15 | 14 | 14 | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 0 | 14 | 10 | 32 | 32 | 32 | 12 | 0 | 7 | 0 | 0
svc | BHemphill | TOTAL Avail: BHemphill |  | 40 | 20 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 46 | 20 | 8 | 7 | 3 | 7 | 5 | 2 | -5 | 2 | 2

## allocation-dev
Resource | Func. | Total lbl for lookup | Project | Activity/Task | 2015-09-27 | 10/4 | 10/11 | 10/18 | 10/25 | 11/1 | 11/8 | 11/15 | 11/22 | 11/29 | 12/6 | 12/13 | 12/20 | 12/27 | 1/3 | 1/10
BObama | fdev | fdev | Bugs-Defects | Bug Fixes, Mega Menus |  |  | 8 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
BObama | fdev | fdev | Dynamic Size Chips | Design | 10/4: 32; 10/11: 24; 10/18: 24
BObama | fdev | fdev | Bugs-Enhancements
BObama | fdev | fdev | Redesign: KR |  |  |  | 0 | 8 | 2 | 3 | 4 | 5 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
BObama | fdev | fdev | OoO |  | 2015-09-27: 32
BObama | fdev | fdevT | TOTAL Avail: BObama |  | 0 | 0 | 0 | 0 | 10 | 9 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WSmith | fdev | fdev | ARC Pricing and Promo project | Misc. | [6 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 2 | 2
WSmith | fdev | fdev | Redesign: JP |  |  | 24 | 8 | 8 | 8 | 20 | 10 | 10 | 10 | 10 | 10 | 1 | 2 | 3 | 5 | 6
WSmith | fdev | fdev | Redesign: KR |  |  |  |  | 24 | 24 | 12 | 12 | 12 | 12 | 12 | 12 | 33 | 2 | 2 | 3 | 12
WSmith | fdev | fdev | Checkout Redesign US
WSmith | fdev | fdev | OoO |  | 2015-09-27: 32
WSmith | fdev | fdevT | TOTAL Avail: WSmith |  | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 18 | 25 | 22 | 12
JLong | bdev | bdev | SAP Implementation | AU/JP/Global |  | 16 | 24 | 24 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JLong | bdev | bdev | Bugs-Defects |  | 10/4: 2; 10/11: 1; 10/18: 1; 10/25: 1
JLong | bdev | bdev | Marketplaces | [6 empty] | 20 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
JLong | bdev | bdev | Cart Improvements, Phase 1 |  | 10/18: 14
JLong | bdev | bdev | SAP Meetings | B2C |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JLong | bdev | bdev | CRM Data Capture EU/AP |  |  | 10 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
JLong | bdev | bdev | OoO |  | 2015-09-27: 32
JLong | bdev | bdevT | TOTAL Avail: JLong |  | 0 | 0 | -1 | -15 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SJones | bdev | bdev | Bugs-Defects | Misc. |  | 12 | 12 | 12 | 11 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
SJones | bdev | bdev | SAP Implementation | AU go live | bar: 10/25
SJones | bdev | bdev | eCom CFT | Rechartering | bar: 10/25
SJones | bdev | bdev | OoO |  | 2015-09-27: 16
SJones | bdev | bdevT | TOTAL Avail: SJones |  | 16 | 20 | 20 | 20 | 19 | 22 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
MSimpson | qa | qa | US Checkout Redesign |  | 5 | 4 | 3 | 7 | 2 | 9 | 7 | 6 | 2 | 9 | 3 | 8 | 2 | 2 | 2 | 7
MSimpson | qa | qa | Improved newsletter registration |  | 8 | 8 | 5 | 2 | 5 | 10 | 9 | 8 | 6 | 10 | 3 | 2 | 2 | 2 | 8 | 2
MSimpson | qa | qa | Cart Ikp | UAT/Build testing | 8 | 8 | 1 | 3 | 8 | 2 | 9 | 9 | 8 | 4 | 3 | 7 | 7 | 6 | 3 | 5
MSimpson | qa | qa | QA Builds/Projects | UAT/Build testing | 4 | 3 | 1 | 1 | 9 | 3 | 2 | 6 | 6 | 7 | 5 | 4 | 10 | 9 | 6 | 9
MSimpson | qa | qa | Regressionq | Release regression testing | 9 | 7 | 9 | 6 | 3 | 3 | 4 | 5 | 8 | 5 | 2 | 2 | 3 | 7 | 7 | 6
MSimpson | qa | qa | Product Sets |  | 7 | 4 | 5 | 5 | 3 | 1 | 3 | 2 | 7 | 5 | 7 | 5 | 10 | 6 | 5 | 4
MSimpson | qa | qa | OoO |  | 3 | 3 | 1 | 7 | 3 | 5 | 5 | 7 | 2 | 10 | 10 | 5 | 4 | 10 | 6 | 1
MSimpson | qa | qaT | TOTAL Avail: MSimpson |  | -12 | -5 | 7 | 1 | -1 | -1 | -7 | -11 | -7 | -18 | -1 | -1 | -6 | -10 | -5 | -2
EPresley | qa | qa | Automated Regression |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
EPresley | qa | qa | Redesign: JP |  |  | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
EPresley | qa | qa | QA Builds/Projects | UAT Build Testing |  | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
EPresley | qa | qa | CRM Data Capture EU/AP |  |  | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EPresley | qa | qa | Cart Improvements, Phase 1 |  |  |  |  | 14 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EPresley | qa | qa | OoO |  | 2015-09-27: 32
EPresley | qa | qaT | TOTAL Avail: EPresley |  | 0 | 2 | 11 | -4 | 8 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2

## allocation-pm
Resource | Func. | Total lbl for lookup | Project | Activity/Task | 2015-09-27 | 10/4 | 10/11 | 10/18 | 10/25 | 11/1 | 11/8 | 11/15 | 11/22 | 11/29 | 12/6 | 12/13 | 12/20 | 12/27 | 1/3 | 1/10
KUrban | pm | pm | CRM Data Capture EU/AP |  |  | 8 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
KUrban | pm | pm | Americas Phase 1 XYZ |  |  | 8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
KUrban | pm | pm | Team Management |  |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
KBaltus | pm | pm | OoO |  | 2015-09-27: 32; 10/4: 8
KBaltus | pm | pmT | TOTAL Avail: KBaltus |  | 0 | 8 | 12 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
KKardashian | pm | pm | Team Management | Adminsitrative stuff |  | 10 | 15 | 15 | 15 | 13 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
KKardashian | pm | pm | eCom CFT | BRT for Content sharing |  | 4 | 4 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
KKardashian | pm | pm | NPI | Training/Support |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
KKardashian | pm | pm | Site Performance Improvements, Q2 | Regional Team Monitors |  | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KKardashian | pm | pm | Size Chart Rollout | Work on the conversion and getting regions on board |  | 10 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
KKardashian | pm | pm | Jira Implementation | Proof of Conscept + Business Case | bar: 10/4 to 1/10
KKardashian | pm | pm | OoO |  | 32 | [5 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
KKardashian | pm | pmT | TOTAL Avail: KKardashian |  | 0 | 1 | 3 | -1 | -1 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5

## allocation-creative
Resource | Func. | Total lbl for lookup | Project | Activity/Task | 2015-09-27 | 10/4 | 10/11 | 10/18 | 10/25 | 11/1 | 11/8 | 11/15 | 11/22 | 11/29 | 12/6 | 12/13 | 12/20 | 12/27 | 1/3 | 1/10
MJackson | copy | copy | Redesign ABC | Home Page | 1 | 7 | 5 | 2 | 6 | 6 | 7 | 3 | 5 | 6 | 5 | 2 | 7 | 2 | 4 | 4
MJackson | copy | copy | Redesign 123 |  | 9 | 4 | 4 | 5 | 6 | 5 | 4 | 4 | 5 | 8 | 7 | 2 | 8 | 2 | 5 | 6
MJackson | copy | copy | Landing Page TAB |  | 7 | 7 | 4 | 8 | 5 | 5 | 8 | 6 | 2 | 7 | 8 | 8 | 7 | 5 | 6 | 7
MJackson | copy | copy | SEO 2014 |  | 6 | 6 | 4 | 3 | 5 | 3 | 3 | 4 | 8 | 4 | 4 | 4 | 7 | 3 | 7 | 5
MJackson | copy | copy | OoO |  | 2 | 2 | 6 | 2 | 2 | 6 | 2 | 7 | 2 | 4 | 4 | 2 | 3 | 8 | 2 | 6
MJackson | copy | copyT | TOTAL Avail: MJackson |  | 7 | 6 | 9 | 12 | 8 | 7 | 8 | 8 | 10 | 3 | 4 | 14 | 0 | 12 | 8 | 4
JJackson | des | des | Redesign ABC |  | 1 | 5 | 10 | 5 | 2 | 0 | 4 | 7 | 10 | 6 | 2 | 8 | 3 | 5 | 2 | 7
JJackson | des | des | Redesign 123 |  | 10 | 5 | 2 | 9 | 8 | 10 | 10 | 5 | 5 | 3 | 4 | 2 | 8 | 10 | 4 | 6
JJackson | des | des | Landing Page TAB |  | 0 | 0 | 10 | 6 | 2 | 6 | 9 | 8 | 9 | 9 | 0 | 8 | 5 | 0 | 6 | 6
JJackson | des | des | OoO |  | 7 | 7 | 9 | 9 | 4 | 2 | 5 | 0 | 3 | 2 | 8 | 10 | 6 | 8 | 4 | 5
JJackson | des | des | SEO 2014 |  | 0 | 5 | 3 | 5 | 0 | 3 | 4 | 9 | 10 | 4 | 10 | 1 | 1 | 9 | 4 | 2
JJackson | des | desT | TOTAL Avail: JJackson |  | 14 | 10 | -2 | -2 | 16 | 11 | 0 | 3 | -5 | 8 | 8 | 3 | 9 | 0 | 12 | 6
HJackman | ux | ux | Demandware A/B Tests | Optimization Tests | 9 | 9 | 10 | 1 | 9 | 2 | 7 | 10 | 1 | 3 | 3 | 2 | 1 | 0 | 9 | 0
HJackman | ux | ux | Monetate Program | Optimization Tests | 9 | 4 | 0 | 8 | 1 | 7 | 9 | 3 | 0 | 6 | 0 | 1 | 4 | 1 | 8 | 5
HJackman | ux | ux | Hi Conversion POC | Optimization Tests | 0 | 2 | 0 | 3 | 9 | 7 | 4 | 2 | 10 | 3 | 8 | 5 | 4 | 1 | 7 | 8
HJackman | ux | ux | Bugs-Enhancements | Misc | 3 | 0 | 6 | 6 | 7 | 2 | 10 | 9 | 2 | 6 | 0 | 6 | 5 | 9 | 10 | 1
HJackman | ux | ux | Redesign: JP/KR/BR General | Wireframe Management | 6 | 0 | 3 | 8 | 3 | 0 | 8 | 0 | 0 | 0 | 5 | 3 | 6 | 8 | 4 | 3
HJackman | ux | ux | Cart Improvements, Phase 1 |  | 5 | 0 | 10 | 2 | 8 | 7 | 4 | 9 | 3 | 6 | 5 | 5 | 5 | 1 | 7 | 10
HJackman | ux | ux | OoO |  | 5 | 3 | 7 | 9 | 0 | 3 | 4 | 9 | 3 | 10 | 2 | 0 | 8 | 5 | 10 | 10
HJackman | ux | uxT | TOTAL Avail: HJackman |  | -5 | 14 | -4 | -5 | -5 | 4 | -14 | -10 | 13 | -2 | 9 | 10 | -1 | 7 | -23 | -5

## allocation-archive-2013 (hidden)
Team | Func. | Total lbl for lookup | Resource | Project | Activity | 2013-05-19 | 5/26 | 6/2 | 6/9 | 6/16 | 6/23 | 6/30 | 7/7 | 7/14 | 7/21 | 7/28 | 8/4 | 8/11 | 8/18 | 8/25 | 9/1 | 9/8 | 9/15 | 9/22 | 9/29 | 10/6 | 10/13 | 10/20 | 10/27 | 11/3 | 11/10 | 11/17 | 11/24 | 12/1 | 12/8 | 12/15 | 12/22 | 12/29 | 1/5 | 1/12 | 1/19 | 1/26 | 2/2 | 2/9 | 2/16 | 2/23 | 3/2 | 3/9 | 3/16 | 3/23 | 3/30 | 4/6
dev | dw | dw | CMcGinnie | Bugs-Defects | Bug Fixes, Mega Menus | 32 | 32 | 32 | 32 | 32 | 9 | 16 | 16 | 16 | 16 | 16 | 12 | 0 | 12 | 6 | 12 | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 32 | 10 | 20 | 4 | 10 | 10 | 10 | 10 | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
dev | dw | dw | CMcGinnie | Dynamic Size Chips | Design | [5 empty] | 23 | 8 | 16 | 16 | 8 | 16 | 20 | 32 | 20 | 6 | 14 |  | 24 | 24 | 24 | 24 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 32
dev | dw | dw | CMcGinnie | Mobile Site Global Rollout | retina color chip production | [26 empty] | 6 |  |  | 8
dev | dw | dw | CMcGinnie | Bugs-Enhancements | [6 empty] | 23 | 8 | 16 | 16 | 8 | 16 | 20 | 32 | 20 | 6 | 14 |  | 24 | 24 | 24 | 24 | 22 | 24 |  | 22 | 12 | 12 |  | 12 | 4
dev | dw | dw | CMcGinnie | Redesign: KR | [6 empty] | 23 | 8 | 16 | 16 | 8 | 16 | 20 | 32 | 20 | 6 | 14 |  | 24 | 24 | 24 | 24 | 22 | 24 |  |  |  | 10 | 4 | 10 | 10 | 16 |  |  |  | 24 | 24 | 24 | 12
dev | dw | dw | CMcGinnie | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  |  |  |  | 20 | 6 | [11 empty] | 18 |  |  | 6 | 32 | 32
dev | dw | dwT | CMcGinnie | TOTAL Avail: CMcGinnie |  | 0 | -7 | 0 | 0 | 0 | -46 | -16 | -32 | -32 | -8 | -32 | -40 | -64 | -40 | -12 | -28 | 0 | -48 | -48 | -48 | -48 | -22 | -26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
dev | dw | dw | AJuretus | Bugs-Defects | Misc. | 30 | 30 | 32 | 32 | 32 | 9 | 16 | 16 | 16 | 16 | 8 | 24 | 24 | 12 | 12 | 12 | 32 | 8 |  | 8 | 8 | 8 | 8 | 32 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
dev | dw | dw | AJuretus | Bugs-Enhancements | Misc. | [5 empty] | 23 | 8 | 16 | 16 | 16 | 8 | 8 | 8 | 20 | 20 | 14 |  | 24 |  | 18 | 18 | 24 | 24 |  | 22 | 12 | 12 |  | 12 | 12
dev | dw | dw | AJuretus | Redesign: JP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | 10 | 10 | 10 | 10 | 10 | 22 |  |  | 24 | 24 | 24 | 24 | 12
dev | dw | dw | AJuretus | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 16 |  |  |  |  | 6 |  |  | 32 | 6 | 6 | [6 empty] | 12 |  |  |  | 32 | 32
dev | dw | dwT | AJuretus | TOTAL Avail: AJuretus |  | 2 | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
dev | mw | mw | JLong | SAP Implementation | EDW/MW | 4 | 0 | 4 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 14 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 16 | 16 | 24 |  |  | 16 | 16 | 16 | 12 | 12 | 12 | 12 | 16 | 16 | 16 | 16 | 16 | 16
dev | mw | mw | JLong | Bugs-Defects |  | 2 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8
dev | mw |  | JLong | Adyen Rollout for AU | verify AU ship confirm query | [33 empty] | 2
dev | mw |  | JLong | Marketplaces | [37 empty] | 12 | 12 | 12 | 12
dev | mw | mw | JLong | SAP Meetings | B2C | 10 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 14 | 14 | 16 | 16 | 16 | 16 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 16 | 16 | 8 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
dev | mw | mw | JLong | CRM Data Capture EU/AP | [34 empty] | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
dev | mw | mw | JLong | OoO |  | 0 | 32 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | [5 empty] | 6 | [11 empty] | 12 |  |  |  | 32 | 32
dev | mw | mwT | JLong | TOTAL Avail: JLong |  | 16 | 0 | 18 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8 | -8 | -8 | -8 | 0 | 0 | 0 | 0 | 0 | 0 | 32
dev | ops | ops | SDeitz | Bugs-Defects | Misc. | 8 | 8 | 8 | 2 | 12 | 12 | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 4 | 6 | 4 | 12 | 16 | 16 | 4 | 16 | 16 | 16 | 16 | 16 | 16 | 4 | 16 | 16 | 8 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
dev | ops | ops | SDeitz | NPI: SS14 + Outsource | Train Resource/processing | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 10 | 10
dev | ops | FlnameOP | SDeitz | Redesign: JP | [9 empty] | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
dev | ops | ops | SDeitz | Size Chart Rollout | Update Data | 2 | 2 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [15 empty] | 8
dev | ops | ops | SDeitz | CRM Data Capture EU/AP | [34 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 4 | 4 | 4
dev | ops | ops | SDeitz | XYZCompany Club Rewards: eComm Integration and Customer Experience on Web | [31 empty] | 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4
dev | ops | ops | SDeitz | Ops | Misc. | 16 | 16 | 10 | 6 | 16 | 16 | 16 | 16 | 16 | 16 | 18 | 18 | 18 | 18 | 18 | 4 | 16 | 16 | 16 | 16 | 12 | 10 | 16 | 16 | 16 | 16 | 16 | 10 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
dev | ops | ops | SDeitz | OoO |  | 0 | 7 | 0 | 20 | 0 | 0 | 8 | [8 empty] | 12 |  |  |  |  | 16 | 6 | [5 empty] | 18 |  |  |  | 16 | 16
dev | ops | opsT | SDeitz | TOTAL Avail: SDeitz |  | 6 | -1 | 10 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | -1 | -1 | -2 | -2 | 6 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | -4 | -2 | -4 | -4 | -4 | 20
dev | dw | dw | NKuhnel | Bugs-Defects | Misc. | 15 | 6 | 10 | 12 | 6 | 2 | 1 | 3 | 3 | 3 | 0 | 4 | 2 | 10 | 12 | 4 | 12 | 3 | 4 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 |  | 12 | 12 | 15 |  |  | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
dev | dw | dw | NKuhnel | Bugs-Enhancements | Misc. | [5 empty] | 10 | 1 | 3 | 7 | 8 | 4 | 0 | 4 | 0 | 0 |  |  | 7 | 6
dev | dw | dw | NKuhnel | Team Management | Mentoring | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  | 4 | 4 | 4 | 4 |  | 4 | 4
dev | dw | dw | NKuhnel | Email Marketing | ET 2.0 Migration |  |  |  | 2 | 2 | 6 | 0 | 4 | 8 | 8 | 22 | 24 | 22 | 12 | 4 | 4 |  |  |  |  | 4 | 4 |  |  |  |  | 12 |  | 12 | 4
dev | dw | dw | NKuhnel | SAP Card Connect Integration | Sandbox testing |  |  |  | 2 | 2 | 6 | 0 | 4 | 8 | 8 | 22 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | [11 empty] | 4 |  |  | 4
dev | dw |  | NKuhnel | Adyen Rollout for AU | Skin CSS | [33 empty] | 4 | 4 | 0
dev | dw | dw | NKuhnel | Site Performance Optimization | Planning + Development | 16 | 10 | 16 | 12 | 16 | 8 | 2 | 2 | 2 | 0 | 0 |  |  | 4 | 10 | 14 | 24 | 16 | 16 | 16 | 16 | 16 | 15 | 16 | 16 | 16 | 10 |  | 16 | 12 | 12
dev | dw | dw | NKuhnel | CRM Data Capture EU/AP | [34 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2
dev | dw | dw | NKuhnel | XYZCompany Club Rewards: eComm Integration and Customer Experience on Web | [31 empty] | 1 |  |  | 8 | 12 | 16 | 16 | 24 | 24 | 24 | 24 | 24
dev | dw | dw | NKuhnel | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 24 | 16 | 8 | 8 | [5 empty] | 6 | [11 empty] | 32 |  |  |  | 32 | 32
dev | dw | dwT | NKuhnel | TOTAL Avail: NKuhnel |  | -3 | 5 | 2 | 0 | 2 | -4 | 0 | -4 | -8 | -7 | -20 | -2 | -2 | 0 | 0 | 0 | -8 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | -12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | -4 | -4 | -4 | -2 | 22 | 22 | 24 | 24 | 24
dev | dw | dw | Offshore team | Bugs-Defects |  | 80 | 80 | 80 | 136 | 120 | 8 | 100 | 100 | 100 | 100 | 100 | 33 | 46 | 12 | 24 | 60 | 60 | 60 | 60 | 20 | 50 | 86 | 80 | 90 | 70 | 70 | 22 | 70 | 70 | 70 | 30 | 70 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
dev | dw | dw | Offshore team | Bugs-Enhancements | [6 empty] | 12 | 104 | 94 | 40 | 40 | 40 | 0 | 0 | 0 | 0
dev | dw | dw | Offshore team | Regression Testing | Automation | 20 | 20 | 20 | 20 | 20 | 16 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 72 | 40 | 80 | 80 | 40 | 60 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0 | 48 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
dev | dw | dw | Offshore team | Checkout Redesign US |  | 20 | 20 | 20 | 20 | 20 | 16 | 80 | 80 | 80 | 80 | 80 | 100 | 100 | 97 | 104 | 100 | 100 | 80 | 100 | 80 | 20 | 40
dev | dw | dw | Offshore team | Redesign: JP/KR/BR General | [9 empty] | 0 | 0 | 5 | 11 | 16 | 21 | 27 |  | 16 | 27 | 0 | 0 | 20 | 20 | 60 | 60 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 100 | 80
dev | dw | dw | Offshore team | Improved RMA Messaging | RMA Code refactor | 0 | 0 | 0 | 8 | 20 | 20 | 10 | 20 | 20 | 20 | 30 | 50 | 50 | 50 | 25 | 8 | 8 | 12 | 40 | 40 | 10 | 4
dev | dw | dw | offshore team | Spec writing | Checkout Opt Docs | [9 empty] | 16 | 4 | 2 | [5 empty] | 20
dev | dw |  | offshore team | GL MarketPlace initiatives | catalog dev | [33 empty] | 0 | 20 | 40 | 40 | 20 | 10
dev | dw |  | offshore team | Team Management | Kiev Lead | [21 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
dev | dw |  | offshore team | SAP Card Connect Integration | [38 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0
dev | dw | dw | Offshore team | OoO |  | 0 | 0 | 0 | 0 | 8 | 112 | 0 | 0 | 8 | 16 | 40 | 24 | 8 | 40 | 40 | 16 | 60 |  |  | 80 | 80 |  |  |  |  | 0 | 48 |  |  |  | 40 | 80 | 72
dev | dw | dwT | Offshore team | TOTAL Avail: Offshore team |  | 60 | 60 | 60 | -4 | -8 | -4 | -74 | -74 | -28 | -52 | -79 | 0 | 0 | 0 | 0 | 44 | -4 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 70 | 70 | 10 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 120
dev | ops | ops | PMcElroy | Bugs/Maintenance |  | 0 | 0 | 10 | 8 | 2 | 10 | 0 | 12 | 12 | 6 | 12 | 5 | 15 | 16 | 16 | 8 | 14 | 16 | 12 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 4
dev | ops | ops | PMcElroy | SAP Card Connect Integration |  | 0 | 0 | 4 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 |  | 2 | 2 | 2 |  |  |  | 2 | [6 empty] | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
dev | ops | ops | PMcElroy | Site Performance Optimization | Oversight of team |  |  | 4 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 1 | 0 | 4 | 3 | 2 | 2 | 24 | 2 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2
dev | ops | ops | PMcElroy | ops | ops |  |  |  | 6 |  |  |  | 8 | 8 | 8 | 12 | 0 | 6 | 8 | 8 | 12 | 8 | 12 | 4 | 6 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 12 | 12 | 4 | 16 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
dev | ops | ops | PMcElroy | GL MarketPlace initiatives | ChannelAdvisor Meeting | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 2
dev | ops | ops | PMcElroy | Redesign: JP/KR/BR General | Kickoff meeting with BR | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 5 | 2 |  | 4 | 4 | 2 | 2 | 2 | 4 | 2 | 6 | 2 | 4 | 4 | 4 | 6 | 6 | 6 | 6 |  | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
dev | ops | ops | PMcElroy | OoO |  | 0 | 7 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 10 | 0 | 20 | 0 | 0 | 0 | 6 |  |  | 6 | 16 | 4 | [6 empty] | 24 |  |  | 12 | 16 | 16
dev | ops | opsT | PMcElroy | TOTAL Avail: PMcElroy |  | 16 | 14 | 3 | 1 | -3 | -2 | -2 | 0 | -2 | -2 | 3 | 3 | 3 | -1 | 0 | -2 | -24 | -6 | -4 | -2 | 0 | -2 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 4 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 32
pro | pd | pd | KBaltus | Redesign: JP/KR/BR General | Support PM | [8 empty] | 8 | 8 | 4 | 2 | 4 | 4 | 2 | 2 |  | 2 |  |  |  |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2
pro | pd | pd | KBaltus | CRM Data Capture EU/AP | Product Management | [24 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
pro | pd | pd | KBaltus | XYZCompany Club Rewards: eComm Integration and Customer Experience on Web | Product Management | [29 empty] | 4 | 4 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
pro | pd | pd | KBaltus | Mobile Site Global Rollout | Product Management |  |  |  | 8 | 10 | 8 | 4 | 11 | 11 | 11 | 4 | 11 | 11 | 11 | 11 | 4 | 11 | 11 | 6 | 11 | 15 | 16 | 15 | 15 | 11 | 11 | 25 | 11 | 18 | 18 | 18 |  |  | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 0
pro | pd | pd | KBaltus | OoO |  | 7 | 7 | 0 | 0 | 0 | 10 | 24 |  |  |  |  | 12 |  |  |  | 12 |  | 6 | 12 | 6 | [7 empty] | 12 |  |  |  | 32 | 32 | 8
pro | pd | pdT | KBaltus | TOTAL Avail: KBaltus |  | 25 | 25 | 32 | 24 | 22 | 14 | 4 | 21 | 13 | 13 | 24 | 7 | 17 | 17 | 19 | 14 | 21 | 13 | 14 | 15 | 17 | 16 | 15 | 17 | 15 | 15 | 1 | 3 | 8 | 4 | 4 | 0 | 0 | -5 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 13 | 13 | 13 | 13 | 21 | 32
per | oth | oth | JComstock |  |  | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
per | oth | oth | JComstock | NPI | Bugs | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
per | oth | oth | JComstock | OoO |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 |  |  |  |  | 6
per | oth | othT | JComstock | TOTAL Avail: JComstock |  | -15 | -15 | 0 | 0 | 0 | 0 | -8 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | -1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
per | pm | pm | JZapin | Team Management | GoalSetting + Reorg Transition | 2 | 2 | 10 | 10 | 10 | 10 | 10 | 5 | 10 | 10 | 20 |  | 2 | 4 | 4 | 5 | 5 | 5 | 5 | 0 | 10 | 10 | 10 | 16 | 10 | 10 | 15 | 6 | 10 | 15 | 10 |  |  | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0
per | pm | pm | JZapin | 2014 Roadmap |  | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  | 5 |  |  | 5
per | pm | pm | JZapin | Cart Level Upsell | Oversee Project | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
per | pm | pm | JZapin | eCom CFT | Charter | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 |  | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 |  |  | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
per | pm | pm | JZapin | NPI: SS14 + Outsource | Training/Support | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 2 |  | 2 | 5 | 10 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 2 | 5 | 5 | 3 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
per | pm | pm | JZapin | NPI | Getting more product content | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 2 |  | 2 | 5 | 10 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
per | pm | pm | JZapin | SAP Card Connect Integration |  | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 5 | 5 | 0 | 0 |  | 0 | 4 | 4 | 4 | 10 | 4 | 4 | 2 | 4 | 4 | 5 | 5 | 5 | 5 | 2 | 2 |  | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 0
per | pm | pm | JZapin | Size Chart Rollout | Work on the conversion and getting regions on board | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 5 | 5 | 0 | 0 |  | 0 | 4 | 4 | 4 | 10 | 4 | 4 | 2 | 4 | 4 | 5 | 5 | 1 | 1 | 1 | 1 |  | 8 | 10 |  |  | 10
per | pm | pm | JZapin |  |  | 3 | 3 | 3 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 1 |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 |  | 4 | 1 | 2 | 2 |  | 2 | 2 | 2
per | pm | pm | JZapin | Redesign: JP/KR/BR General |  | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 5 | 2 | 2 |  | 5 | 5 | 7 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
per | pm | pm | JZapin | OoO |  | 7 | 7 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 32 | 7 | 7 |  | 6 |  |  |  | 24 | [7 empty] | 12 |  |  |  | 32 | 32
per | oth | othT | JZapin | TOTAL Avail: JZapin |  | -26 | -16 | -11 | -11 | -16 | -10 | -20 | -23 | -21 | -2 | -1 | 0 | 10 | -14 | -18 | -14 | -20 | -8 | -8 | -3 | -7 | -6 | -6 | -15 | -3 | -3 | -3 | -2 | 5 | -5 | -6 | 0 | 0 | -6 | 4 | 2 | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 32
pro | pd | pd | BCalandra | GL MarketPlace initiatives |  | 3 | 3 | 3 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 1 |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 |  | 4 | 1 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 14 | 14 | 14 | 14 | 10 | 10 | 10 | 10 | 8 | 8
pro | pd | pd | BCalandra | ProductFinder | [31 empty] | 5 |  |  | 11 | 11 | 10 | 10 | 2 | 2 | 2 | 2
pro | pd |  | BCalandra | Adyen Rollout for AU | [31 empty] | 5 |  |  | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6
pro | pd | pd | BCalandra | Bi-Weekly eCom Training | Orientation | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 5 | 2 | 2 |  | 5 | 5 | 7 | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 5 | 5 | 8 | 8 | 5 | 2
pro | pd | pd | BCalandra | OoO |  | 7 | 7 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 32 | 7 | 7 |  | 6 |  |  |  | 24 | [7 empty] | 6 |  |  |  | 16 | 16
pro | pd | pdT | BCalandra | TOTAL Avail: BCalandra | 50% PM | 26 | 16 | 31 | 31 | 28 | 32 | 22 | 25 | 17 | 14 | 23 | -32 | -8 | 2 | 6 | 3 | 9 | 9 | 9 | -24 | 4 | 9 | 8 | 14 | 0 | 0 | 3 | 0 | 8 | 8 | -2 | 0 | 0 | 2 | 2 | 2 | 2 | 14 | 14 | 14 | 14 | 24 | 24 | 32 | 32 | 32 | 32
per | pm | FLnamePM | KSheridan | Redesign: JP/KR/BR General | PM Work | [8 empty] | 0 | 0 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 0 | 0 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 0
per | pm | pm | KSheriden | OoO |  | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | [15 empty] | 9.5 | 9.5
per | pm | pmT | KSheriden | TOTAL Avail: KSheriden |  | 0 | 0 | 4 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
svc | an | an | MCrenshaw | Various e-marketing data / report extracts | PPC Dashboards, EU Reporting | [8 empty] | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
svc | an | an | MCrenshaw | PPC Analysis/Recommendations | PPC Management: APAC & EU | [9 empty] | 14 | 14 | 14 | 9 | 20 | 20 | 14 | 9 | 20 | 20 | 14 | 9 | 20 | 20 | 14 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
svc | an | an | MCrenshaw | Front End Ops: Sorting, Search, Merch, Content | SSO | [9 empty] | 10 | 10 | 10 | 15 | 4 | 4 | 10 | 15 | 4 | 4 | 10 | 15 | 4 | 4 | 10 | 15 | 4 | 4
svc | an | an | MCrenshaw | OoO |  | 32 | 32 | 0 | 0 | 0 | 8 | 16 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | [15 empty] | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
svc | an | anT | MCrenshaw | TOTAL Avail: MCrenshaw |  | -18 | -18 | 4 | 4 | 8 | -5 | 1 | 25 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 32
svc | an | an | WChambers | Team Management |  | 10 | 10 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
svc | an | an | WChambers | Global Performance Dashboard - SOW 2 |  | 5 | 5 | 0 | 0 | 0 | 0 | 0
svc | an | an | WChambers | Tag Management: Marketing |  | 5 | 5 | 5 | 0 | 0 | 0 | 0
svc | an | an | WChambers | Omniture First Party Cookies |  |  |  |  | 5 | 5 | 5 | 5 | 2 | 5 | 5 | 10 | 5
svc | an | an | WChambers | PPC Analysis/Recommendations |  | 5 | 5 | 10 | 10 | 10 | 10 | 15 | 20 | 15 | 20 | 15 | 20 | 25 | 25 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
svc | an | an | WChambers | Various e-marketing data / report extracts |  | 10 | 10 | 10 | 15 | 15 | 15 | 5 | 10 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
svc | an | an | WChambers | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | [5 empty] | 6 | [9 empty] | 12 | [5 empty] | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
svc | an |  | WChambers | Summit 2013 | Prep and Participation | [9 empty] | 5 | 8
svc | an | anT | WChambers | TOTAL Avail: WChambers |  | -3 | -10 | 2 | 0 | 0 | 0 | -3 | -2 | -5 | -5 | -8 | 0 | 0 | 0 | 0 | -1 | 5 | -3 | 2 | 5 | 5 | -5 | -5 | -5 | 0 | -12 | 0 | 0 | 0 | 0 | 0 | -2 | -2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 32
svc | ux | ux | HNemann | Cart Level Upsell | Create wireframes | 6 | 0 | 0 | 6 | 6 | 6 | 6 |  |  |  |  | 16 | 14 | 12 | 10 | 8 | 6 | 8 | [5 empty] | 0 | 10 | 10 | 2 | 2 | 2
svc | ux | ux | HNemann | Redesign: General | Shopping Cart | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [22 empty] | 12 | 12
svc | ux | ux | HNemann | Bugs-Enhancements | Misc | [10 empty] | 8 |  |  | 6 | 2 | 4 | 2 | 2 |  |  | 6 |  | 8 | 4 | 4 | 4 | 6 | 0 | 12 | 8 | 8
svc | ux | ux | HNemann | Mobile Site Global Rollout | UX and Design reviews | 11 | 6 | 0 | 6 | 6 | 6 | 6 |  |  | 0 | 0 | 10 | 10 |  | 0 |  |  | 2 | 8 |  |  | 10 | 8 | 10 | 8 | 4 | 8 | 4 | 8
svc | ux | ux | HNemann | XYZCompany Club Rewards: eComm Integration and Customer Experience on Web | [31 empty] | 1 |  |  | 16 | 15 | 13 | 12 | 11 | 9 | 8 | 7
svc | ux | ux | HNemann | Redesign: JP/KR/BR General | Wireframe Production | [8 empty] | 0 | 0 |  | 0 | 3 | 2 |  |  | 2 | 2 | 2 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6
svc | ux | ux | HNemann | Customer Service weekly CFT meeting | Quarterly CSR Outreach | 2 | 2 | 0 | 2 | 2 | 2 | 2
svc | ux | ux | HNemann | Product Finder: Discovery | Viget Review | [8 empty] | 8 | 8 | 4 | 2 | 4 | 4 | 2 |  | 2 |  | 2 |  |  |  | 2
svc | oth | oth | HNemann | Demandware A/B Tests | Optimization Tests | 9 | 4 | 0 | 0 | 4 | 4 | 4 |  |  | 2 | 3 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 6 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
svc | oth | oth | HNemann | Hi Conversion POC | Optimization Tests | [9 empty] | 4 | 5 |  |  | 6 | 10 | 8 | 10 | 6 | 6 | 1 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
svc | oth | oth | HNemann | Monetate Program | Optimization Tests | [9 empty] | 4 | 5 |  |  | 6 | 10 | 8 | 10 | 6 | 6 | 1 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
svc | ux | ux | HNemann | OoO |  | 0 | 7 | 32 | 0 | 0 | 0 | 20 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 12 | 6 | 6 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 18 | 12 | 12 | 6 | 32 | 32 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
svc | ux | uxT | HNemann | TOTAL Avail: HNemann |  | 4 | 13 | 0 | 18 | 14 | 14 | -6 | 32 | 24 | 8 | 1 | -2 | -5 | -16 | -14 | -14 | -12 | -6 | -10 | 15 | -6 | -6 | -7 | -3 | -11 | -7 | -5 | -7 | -17 | -15 | -10 | 0 | 0 | -2 | -1 | 7 | 5 | 6 | 8 | 9 | 10 | 17 | 17 | 17 | 17 | 17 | 17
svc | ux | dw | Offshore team | Redesign: JP/KR/BR General | Wireframes | 0 | 0 | 0 | 8 | 20 | 20 | 10 | 20 | 20 | 20 | 30 | 50 | 50 | 50 | 25 | 8 | 8 | 12 | 40 | 40 | 10 | 30 | 30 | 30
svc | ux | dw | offshore team | Checkout Redesign US | Wireframes | [9 empty] | 16 | 4 | 2 | [5 empty] | 20 | [5 empty] | 0 | 30
svc | ux | dw | offshore team | Bugs-Enhancements | Wireframes | [9 empty] | 16 | 4 | 2 | [5 empty] | 20 | [5 empty] | 10 | 10
svc | ux | dw | Offshore team | OoO |  | 0 | 0 | 0 | 0 | 8 | 112 | 0 | 0 | 8 | 16 | 40 | 24 | 8 | 40 | 40 | 16 | 60 |  |  | 80 | 80
svc | ux | uxT | Offshore team | TOTAL Avail: Offshore team |  | 60 | 60 | 60 | -4 | -8 | -4 | -74 | -74 | -28 | -52 | -79 | 0 | 0 | 0 | 0 | 44 | -4 | 1 | 0 | 0 | 0 | 0 | 0 | -10 | -10 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
per | qa | qa | MSampson |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
per | qa | qa | MSampson | Email Marketing |  | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
per | qa | qa | MSampson | XYZCompany club digital interface and data routing |  |  |  |  | 1 | 3 | 4 | 0 | 7 | 8 | 9 | 0 | 0 | 13 | 15 | 20
per | qa | qa | MSampson | QA Builds/Projects | UAT/Build testing | 20 | 20 | 20 | 20 | 20 | 5 | 8 | 8 | 20 | 15 | 20 | 20 | 15 | 15 | 4 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 30 | 20 | 20 | 20
per | qa | qa | MSampson | OoO |  | 0 | 7 | 0 | 0 | 0 | 24 | 16 | 16 | [7 empty] | 6 | [10 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
per | qa | qaT | MSampson | TOTAL Avail: MSampson |  | 7 | 0 | 7 | 6 | 4 | -3 | 6 | -1 | 2 | 6 | 10 | 10 | 2 | 0 | 6 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 32 | 32 | 32
per | qa | qa | PRana | Training |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 5 | 3 | 5 | 5
per | qa | qa | PRana | Email Marketing |  | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5
per | qa |  | PRana | GL MarketPlace initiatives | [40 empty] | 21 | 21
per | qa |  | PRana | Adyen Rollout for AU | [36 empty] | 5 | 5 | 5
per | qa | qa | PRana | XYZCompany club digital interface and data routing |  |  |  |  | 1 | 3 | 4 | 0 | 7 | 8 | 9 | 0 | 0 | 13 | 15 | 20
per | qa | qa | PRana | QA Builds/Projects | UAT/Build testing | 20 | 20 | 20 | 20 | 20 | 5 | 8 | 8 | 20 | 15 | 20 | 20 | 15 | 15 | 4 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 30 | 20 | 20 | 20 | 20 | 10 | 20 | 20 | 20
per | qa | qa | PRana | OoO |  | 0 | 7 | 0 | 0 | 0 | 24 | 16 | 16 | [7 empty] | 6 | [11 empty] | 12 |  |  |  | 32 | 32
per | qa | qaT | PRana | TOTAL Avail: PRana |  | 7 | 0 | 7 | 6 | 4 | -3 | 6 | -1 | 2 | 6 | 10 | 10 | 2 | 0 | 6 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 2 | 2 | 2 | 2 | 7 | 0 | 0 | 32 | 32 | 27 | 27 | 27 | 32 | 11 | 11 | 32 | 32 | 32 | 32 | 32 | 32
per | qa | qa | JGeditz | Checkout Redesign US | Demo of Checkout with Astound | 2 | 2 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2 | 2 | 2 | 10 | 10
per | qa | qa | JGeditz | Automated Regression |  | 2 | 2 | 4 | 2 | 2 | 2 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
per | qa | qa | JGeditz | Redesign: JP | [9 empty] | 0 | 0 | 1 | 0 | 4 | 5 | 7 |  | 7 | 8 | 10 | 13 | 15 | 16 | 0 | 0 | [9 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
per | qa | qa | JGeditz | Mobile Site Global Rollout | CA Tablet | [27 empty] | 8 |  | 8
per | qa | qa | JGeditz | Mobile Site Global Rollout | DE, AU, CA Smartphone | [27 empty] | 8 |  | 16
per | qa | qa | JGeditz | QA Builds/Projects | UAT Build Testing | 20 | 20 | 20 | 15 | 12 | 11 | 0 | 18 | 25 | 25 | 20 | 25 | 25 | 24 | 22 | 15 | 12 | 18 | 17 | 6 | 4 | 5 | 0 | 29 | 29 | 29 | 20 | 0 | 20 |  | 20 |  |  | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 20 | 20 | 20
per | qa | qa | JGeditz | CRM Data Capture EU/AP | [34 empty] | 1 | 2 | 3 | 3 | 4 | 5 | 5 | 6 | 7 | 7 | 8
per | qa | qa | JGeditz | XYZCompany Club Rewards: eComm Integration and Customer Experience on Web | [31 empty] | 1 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9
per | qa |  | JGeditz | Training | [27 empty] | 5 | 3 | 5 | 5 | 5
per | qa | qa | JGeditz | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 32 | [8 empty] | 6 | 8 |  |  |  |  | 8 | 32 |  |  |  |  | 12 |  |  |  | 32 | 32
per | an |  | JGeditz | Summit 2013 | Prep and Participation | [9 empty] | 2 | 6
per | qa | qaT | JGeditz | TOTAL Avail: JGeditz |  | 8 | 1 | 8 | 15 | 18 | 19 | 0 | 12 | 4 | 2 | 2 | 4 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | -2 | 4 | 0 | 3 | 0 | 0 | 1 | 9 | 7 | 6 | 4 | 2 | 1 | 0 | 6 | 6 | 5 | 3 | 3 | 9
pro | pd | pd | MFrance | NPI |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
pro | pd | pd | MFrance | Team Management | Coord. Training | 10 | 10 | 5 | 5 | 5 | 2 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
pro | pd | pd | MFrance | Split Testing: Planning, Setup, Reporting | [9 empty] | 5 | 2 | 5 | 2 | 5 | 2 | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
pro | pd | pd | MFrance | Front End Ops: Sorting, Merch, Content | [9 empty] | 10 | 0 | 3 | 8 | 8 | 8 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
pro | pd | pd | MFrance | Demandware Outreach/Regional Site Manager Support |  | 20 | 5 | 20 | 20 | 20 | 20 | 12 | 17 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
pro | pd | pd | MFrance | Email Marketing |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
pro | pd | pd | MFrance | Bugs/Maintenance |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10 | 0 | 20 | 15 | 12 | 15 | 17 | 20 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
pro | pd | pd | MFrance | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 28 | [5 empty] | 6 | [15 empty] | 32 | 32 | 1 1: 32
pro | pd | pdT | MFrance | TOTAL Avail: MFrance |  | -8 | 0 | -3 | -5 | -5 | -2 | -4 | -4 | 1 | -2 | 0 | 0 | 0 | 0 | -2 | -8 | 0 | -2 | 0 | 0 | 0 | 0 | -5 | -5 | -5 | -5 | -5 | -5 | -5 | -5 | -5 | 0 | 0 | 0 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
svc | ba | ba | KSheridan | Redesign: JP/KR/BR General | [9 empty] | 0 | 0 | 10 | 10 | 10 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [5 empty] | 9.5 | 9.5 |  |  | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5
svc | ba | ba | KSheriden | OoO |  | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | [15 empty] | 9.5 | 9.5
svc | ba | baT | KSheriden | TOTAL Avail: KSheriden |  | -2 | -2 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6 | -6 | 0 | 0 | 0 | 0 | 0 | -9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
svc | oth | oth | BHemphill | Team Management |  | 5 | 5 | 12 | 6 | 6 | 6 | 6 | 0 | 6 | [5 empty] | 7 | 7 | 7 | 7 | 7 | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
svc | oth | oth | BHemphill | Mobile Site Global Rollout | Dashboards/reports | 8 | 8 | 2 | 2 | 4 | 4 | 2 | 0 | [16 empty] | 4 | 5
svc | oth | oth | BHemphill | Redesign: JP/KR/BR General |  | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 5 | 2 |  | 6 |  |  | 2 | 2 |  |  | 2 | [10 empty] | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
svc | oth | oth | BHemphill | Product Finder: Discovery | Viget Review | [8 empty] | 8 | 8 | 4 | 2 | 4 | 4 | 2 |  | 2 | 2 | 2 |  |  |  | 2
svc | oth | oth | BHemphill | MarketPlaces | ChannelAdvisor Meeting | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 2 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | 2
svc | oth | oth | BHemphill | Site Performance Optimization | [16 empty] | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
svc | oth | oth | BHemphill | Demandware Outreach/Regional Site Manager Support |  | 10 | 10 | 8 | 8 | 8 | 8 |  | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 2 | 2 | 2
svc | oth | oth | BHemphill | CRM | signature capture requirements | [24 empty] | 2 | 8
svc | oth | an | BHemphill | Delve Dashboards | [17 empty] | 4 | 4 | 4 | 4 |  |  |  | 4 | 4 | 4 | 4 | 4
svc | oth |  |  | M3 | [16 empty] | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
svc | oth | oth | BHemphill | OoO |  | 0 | 7 | 0 | 0 | 0 | 0 | 16 | 32 | [7 empty] | 6 |  |  |  | 18 | [8 empty] | 16 | 16 |  |  | 32 | 1 1: 32
svc | oth | oth | BHemphill | Tag Management: Marketing |  | 0 | 0 | 10 | 10 | 5 | 5 | 2 | 2 | 2 | 5 | 10 | 15 | 10 | 5 | 2 |  | 10 | 4 | 10 |  | 8 | 8 |  |  | 8 | 8 | 8 | 8
svc | oth | oth | BHemphill | Various e-marketing data / report extracts | nku |  |  | 2 | 5 | 5 | 5 | 5 | 10 | 2 | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 7 | 7 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 10 | 10 | 10 | 10
svc | oth |  | BHemphill | Checkout Redesign US | instrumentation on analytics | [9 empty] | 10 | 24 | 2 | 2 | 2 |  |  | 5 | 3
svc | oth | othT | BHemphill | TOTAL Avail: BHemphill |  | -7 | -9 | -1 | 5 | 3 | 4 | -11 | -24 | -4 | -8 | -21 | -6 | 3 | 4 | -3 | -1 | -13 | -5 | -10 | -3 | 6 | 4 | 10 | 10 | -4 | -11 | -1 | -1 | -5 | -7 | 30 | 32 | 0 | -2 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 32
oth | ba | baT | ContractorBA | Total Avail: ContractorBA | Jason Dunagan- CC Rewards | [24 empty] | 2 | 8 |  |  | 10 |  |  | 2 |  | 16 | 15 | 13 | 12 | 11 | 9 | 8 | 7
oth | ba | baT | ContractorBA | Total Avail: ContractorBA | Jason Dunagan- Epicor EU/AP | [33 empty] | 8 | 7 | 7 | 6 | 5 | 5 | 4 | 3 | 3 | 2 | 1
oth | dw | dwT | ContractorDW | Total Avail: ContractorDW | [17 empty] | 4 | 4 | 4 | 4 |  |  |  | 4 | 4 | 4
oth | mw | mwT | ContractorMW | Total Avail: ContractorMW | [16 empty] | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2
oth | ops | opsT | ContractorOPS | Total Avail: ContractorOPS |  | 0 | 7 | 0 | 0 | 0 | 0 | 16 | 32 | [7 empty] | 6 |  |  |  | 18
oth | pm | pmT | ContractorPM | Total Avail: ContractorPM |  | 0 | 0 | 10 | 10 | 5 | 5 | 2 | 2 | 2 | 5 | 10 | 15 | 10 | 5 | 2 |  | 10 | 4 | 10 |  | 8 | 8 |  |  | 8 | 8
oth | qa | qaT | ContractorQA | Total Avail: ContractorQA |  |  |  | 2 | 5 | 5 | 5 | 5 | 10 | 2 | 5 | 5 | 5 | 5 | 5 | 10 | 10 | 10 | 7 | 7 | 5 | 7 | 7 | 7 | 7 | 7 | 7
oth | ux | uxT | ContractorUX | Total Avail: ContractorUX | [10 empty] | 10 | 24 | 2 | 2 | 2 |  |  | 5 | 3
[9 empty] | 5 | 5 | 5
|  |  |  | Bug- Defects Dev Allocation |  |  |  |  | 220 | 208 | 46 | 143 | 153 | 153 | 153 | 144 | 93 | 92 | 66 | 66 | 94 | 140 | 91 | 88 | 64 | 82 | 130 | 124 | 182 | 118 | 128 | 58 | 94 | 118 | 118 | 73 | 70 | 30 | 54 | 54 | 64 | 64 | 60 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  |  |  | Project & Ehancements Dev Allocation |  |  |  |  | 22 | 40 | 36 | 14 | 28 | 32 | 30 | 54 | 76 | 242 | 230 | 196 | 154 | 140 | 192 | 188 | 178 | 112 | 130 | 124 | 76 | 140 | 120 | 132 | 102 | 132 | 116 | 108 | 80 | 80 | 120 | 96 | 16 | 12 | 12 | 12 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 0
Resources needing assignments

## capacity
offset: | 2 | function: | 10/11/2015 0:00:00 | 10/18 | 10/25 | 11/1 | 11/8 | 11/15 | 11/22 | 11/29 | 12/6 | 12/13 | 12/20 | 12/27 | 1/3 | 1/10 | 1/17 | 1/24
fdev |  |  | 24 | 0 | 10 | 9 | 8 | 7 | 0 | 0 | 0 | -12 | 18 | 25 | 22 | 12 | 0 | 0
bdev |  |  | 19 | 5 | 18 | 22 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 0 | 0
qa |  |  | 18 | -3 | 7 | 5 | -5 | -9 | -5 | -16 | 1 | 1 | -4 | -8 | -3 | 0 | 0 | 0
pm |  |  | 15 | 5 | 5 | 15 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0
ux |  |  | -4 | -5 | -5 | 4 | -14 | -10 | 13 | -2 | 9 | 10 | -1 | 7 | -23 | -5 | 0 | 0
des |  |  | -2 | -2 | 16 | 11 | 0 | 3 | -5 | 8 | 8 | 3 | 9 | 0 | 12 | 6 | 0 | 0
copy |  |  | 9 | 12 | 8 | 7 | 8 | 8 | 10 | 3 | 4 | 14 | 0 | 12 | 8 | 4 | 0 | 0

## capacity-archve (hidden)
SAP Card Connect Integration |  |  | St. Off.
Diff: | 10 | XL size + Dur: | 4
Func. | Resource | alloc type | % Ded
pm | FLnamePM | constant | 100%
dw | FlnameDW | peaks | 200%
mw | FlnameMW | peaks | 20%
ops | FlnameOP | builds | 15%
ux | FLnameUX | tapers | 5%
ba | FLnameBA | tapers | 100%
qa | FLnameQA | builds | 100%
Mobile Site Global Rollout, Wave 2 |  |  | St. Off. | 2014-01-15
Diff: | 5 | M size + Dur: | 2
Func. | Resource | alloc type | % Ded
ba | FLnameBA | tapers | 0%
dw | FlnameDW | tapers | 10%
mw | FlnameMW | peaks | 0%
ops | FlnameOP | builds | 5%
pm | FLnamePM | constant | 25%
qa | FLnameQA | builds | 25%
ux | FLnameUX | tapers | 5%
Promotional Nearness Messaging |  |  | St. Off. | 2014-01-22
Diff: | 7 | L size + Dur: | 3
Func. | Resource | alloc type | % Ded
pm | FLnamePM | constant | 15%
dw | FlnameDW | peaks | 100%
mw | FlnameMW | peaks | 0%
ops | FlnameOP | builds | 20%
ux | FLnameUX | tapers | 50%
ba | FLnameBA | tapers | 50%
qa | FLnameQA | builds | 40%
Cart Level Upsell |  |  | St. Off. | 2014-01-22
Diff: | 7 | L size + Dur: | 3
Func. | Resource | alloc type | % Ded
pm | FLnamePM | constant | 15%
dw | FlnameDW | peaks | 5%
mw | FlnameMW | peaks | 20%
ops | FlnameOP | builds | 10%
ux | FLnameUX | tapers | 7%
ba | FLnameBA | tapers | 10%
qa | FLnameQA | builds | 20%
Global PDP Enhancements, Phase 1 |  |  | St. Off. | 2014-03-13
Diff: | 9 | L size + Dur: | 3
Func. | Resource | alloc type | % Ded
an | FlnameAN | peaks | 0%
ba | FLnameBA | tapers | 10%
dw | FlnameDW | peaks | 100%
mw | FlnameMW | peaks | 100%
ops | FlnameOP | builds | 5%
pd | FlnamePD | peaks | 0%
pm | FLnamePM | constant | 5%
qa | FLnameQA | builds | 20%
ux | FLnameUX | tapers | 0%

## dev-fom (hidden)
|  | Effort | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value
Bug Enhancement (Tier 3 Projects) | FOM | eCom Team |  | Global |  | Status
Bug 8456 - NEW: Tracking pixel MyThings DE/EU/FR/IT/UK | 1.50 | 1 week/contained in 1 system | 2 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Ben
Bug 8078 - Default Lifestyle Image on PDP to #5 Thumb Display | 1.50 | 1 week/contained in 1 system | 2 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Josh
Bug 8047 - research building a category page that is driven solely by certona | 1.25 | 3 weeks/contained in 1 system | 4 | CS: $125K-200K/R: $187.5K-300K | 5 | assigned to nick
Bug 8304 - BR - new payment method (Bradesco) | 1.25 | 3 weeks/contained in 1 system | 4 | CS: $125K-200K/R: $187.5K-300K | 5 | assigned to Brianne
Bug 5151 - Set up functionality so source codes work through the mobile site | 1.00 | 1 week/contained in 1 system | 2 | CS: $25K-50K/R: $37.5K-75K | 2 | pending Nate's test
Bug 8317 - BR - Pardot (Marketing Automation Solution) | 0.75 | 3 weeks/contained in 1 system | 4 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Ben
Bug 8314 - BR - product recommendation tool | 0.75 | 3 weeks/contained in 1 system | 4 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Ben
Bug 8516 - S7 Size Chip R&D | 0.75 | 3 weeks/contained in 1 system | 4 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Corey
Bug 8373 - Implement Site Catalyst Intstrumentation Kit | 0.67 | 1 month/4 + | 6 | CS: $75K-125K/R: $112.5K-187.5K | 4 | assigned to Ben
Bug 8417 - BISN Email Template needs to updated | 0.60 | 2 weeks/contained in 1 system | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Kiev
Bug 8372 - Add new Product Dimension Attributes | 0.60 | 2 weeks/contained in 1 system | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Josh
Bug 8247 - Removal of client side js | 0.60 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Brianne
Bug 8248 - Removal of server side js | 0.60 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Brianne
Bug 7996 - Product Setup | 0.60 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to NPI
Bug 8194 - BR_Offer more than one shipping method based on customer's zip code | 0.60 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Kelly
Bug 8480 - Gigya flow update | 0.60 | 1 month/3 or less systems | 5 | CS: $50K-75K/R: $75K-112.5K | 3 | assigned to Nick
Bug 8151 - Taiwan COD | 0.57 | 1 month/3 or less systems | 7 | CS: $50K-75K/R: $75K-112.5K | 4 | assigned to Brianne
Bug 8023 - Minicart Synchronization Feature | 0.50 | 1 week/contained in 1 system | 4 | CS: $25K-50K/R: $37.5K-75K | 2 | assigned to Kiev
Bug 7654 - Add tracking for Bug#7592 | 0.50 | 1 week/contained in 1 system | 2 | CS: $0-25K/R: $0-37.5K | 1 | Assigned to Ben
Bug 8066 - Add CS toolbox to our X-Tools cartridge | 0.40 | 1 week/contained in 1 system | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | assigned to Kiev
Bug 4980 - Return an Item input Box activate for Canada | 0.33 | 2 weeks/contained in 1 system | 3 | CS: $0-25K/R: $0-37.5K | 1 | assigned to nate
Bug 7134 - Close the ForeSee survey request when the user clicks on the gray portion of the site | 0.20 | 1 week/contained in 1 system | 5 | CS: $25K-50K/R: $37.5K-75K | 1 | assigned to kiev
Bug 8158 - Need to mask the URL of AU site | 0.20 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | assigned to Brianne
Bug 8620 - PDP/Quick Look: Replace In Stock "Status Messaging" with Quantity Remaining Call to Action
Bug 8723 - Check icon for the in stock section
Bug 8713 - Mouseover Text - Style instead of Size
Bug 8675 - Add to Cart button Messaging Update (Redesign Only)
Bug 8608 - Checkout: shippping address page - to change text (AU)
Bug 8621 - UX ¦ Move login to my account/create an account into a pop up
Bug 7531 - 1x1 Tracking Pixel & Click Command Pixel Generating Tool
Bug 8165 - NEW: beslist.nl code snippet required on XYZCompany.nl checkout page
Bug 8702 - Update "Free" messaging in JP cart and checkout to work like the US site
Bug 8745 - content asset / slot at checkout
Bug 8758 - NEW: Option to 'hide' the coupon code field in checkout
Bug 8757 - NEW: Option to disable coupon code input in checkout after use

## capacity-arch (hidden)
Product Sets |  |  | St. Off. | 0 | Excl | N
Diff: | 9 | #REF! | #REF! | wk #
Func. | Resource | alloc type | % Ded | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Tot Hrs | Tot Cost
pm | FLnamePM | constant | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
dw | FlnameDW | peaks | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
mw | FlnameMW | peaks | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ops | FlnameOP | builds | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ux | FLnameUX | tapers | 53% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ba | FLnameBA | tapers | 15% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
qa | FLnameQA | builds | 50% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
KR Virtual Account Bank Transfer Adyen-Inicis |  |  | St. Off. | 0 | Excl | N
Diff: | 8 | #REF! | #REF! | wk #
Func. | Resource | alloc type | % Ded | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Tot Hrs | Tot Cost
pm | FLnamePM | constant | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
dw | FlnameDW | peaks | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
mw | FlnameMW | peaks | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ops | FlnameOP | builds | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ux | FLnameUX | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ba | FLnameBA | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
qa | FLnameQA | builds | 40% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Google Trusted Store |  |  | St. Off. | 0 | Excl | N
Diff: | 7 | #REF! | #REF! | wk #
Func. | Resource | alloc type | % Ded | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Tot Hrs | Tot Cost
pm | FLnamePM | constant | 40% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
dw | FlnameDW | peaks | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
mw | FlnameMW | peaks | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ops | FlnameOP | builds | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ux | FLnameUX | tapers | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ba | FLnameBA | tapers | 30% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
qa | FLnameQA | builds | 40% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## releases (hidden)
Final Feature Build Date | Feature Build # | Original Final Hardening Build Date | Actual Final Hardening Build Date | Original Release Date | Release | Quarter | Points moved to next release | Actual Release Date | Reason for change | Points Released | Bugs Closed | Reopens
12/18/2013 | 193 | 1/1/2014 | - | 2014-01-22 | 194 | Q1 |  | 2014-01-23 | Late UAT Start by Region
1/15/2014 | 195 | 1/29/2014 | - | 2014-02-19 | 196 | Q1 |  | 2014-02-20 | Late UAT Start by Region
2/12/2014 | 197 | 2/26/2014 | 2014-02-28 | 2014-03-19 | 198 | Q1 |  | 2014-03-25 | P1 Cart content development | 11 | 29 | 33
3/12/2014 | 199 | 3/26/2014 |  | 2014-04-16 | 200 | Q2 |  | 2014-04-23 |  | 8 | 49 | 10
4/16/2014 | 201 | 4/30/2014 |  | 2014-05-21 | 202 | Q2 | 5 | 2014-05-19 | Got UAT done early! | 41 | 90 | 15
5/14/2014 | 203 | 5/28/2014 |  | 2014-06-18 | 204 | Q2 | 3 | 2014-06-26 | Large release with complexities | 29 | 53 | 12
6/11/2014 | 205 | 6/25/2014 |  | 2014-07-16 | 206 | Q3 |  |  |  | 16 | 47 | 10
7/16/2014 | 207 | 7/30/2014 |  | 2014-08-20 | 208 | Q3
8/13/2014 | 209 | 8/27/2014 |  | 2014-09-17 | 210 | Q3
9/10/2014 | 211 | 9/24/2014 |  | 2014-10-15 | 212 | Q4
10/8/2014 | 213 | 10/22/2014 |  | 2014-11-12 | 214 | Q4
Note on C1: calculated

## velocity-200 (hidden)
Project | Q? | Size | Points
Mobile Site Global Rollout, Wave 3 | #REF! | M | #REF! | #REF! | = Adjusted from original prioritization
ShoeFinder | #REF! | L | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-q1 (hidden)
Project | Q? | Size | Points | Redesign? | Quarter | Points | w/o Redesign
ExactTarget 2.0 | Q1 | M | #REF! |  | Q1* | #REF!
Site Performance Optimization | Q1 | M | #REF! |  | Q2 | #REF!
Mobile Site Global Rollout, Wave 2 | Q1 | S | #REF! |  | Q3 | 0
Adyen Rollout for AU | #REF! | #REF! | #REF! |  | Q4 | 0
Americas Phase 1 XYZCompany Club Rewards: eComm Integration and Customer Experience on Web | #REF! | #REF! | #REF! |  | *Completed
Cart Improvements, Phase 1 | #REF! | M | #REF!
Cart Improvements, Phase 2: Cart Level Upsell | #REF! | M | #REF!
Checkout Redesign International | #REF! | #REF! | #REF! |  |  | = Adjusted from original prioritization
Checkout Redesign US | #REF! | #REF! | #REF!
CRM Data Capture EU/AP | #REF! | #REF! | #REF!
JP Taxation Change | #REF! | #REF! | #REF! | Y
Merchandising Automation, Phase 1 | #REF! | #REF! | #REF!
Mobile Site Global Rollout, Wave 3 | #REF! | #REF! | #REF!
ShoeFinder | #REF! | #REF! | #REF!
Cart Improvements, Phase 3: Promotional Nearness Messaging | #REF! | M | #REF!
Redesign: BR | Q2 | #REF! | #REF! | Y
Redesign: JP | Q2 | #REF! | #REF! | Y
Redesign: KR | Q2 | #REF! | #REF! | Y
SAP Card Connect Integration | #REF! | #REF! | #REF!
SAP Implementation | Q1 | L | #REF!
US ebay upgrades | #REF! | #REF! | #REF!
Improved newsletter registration workflow APAC | #REF! | #REF! | #REF!
ARC eCom, Phase 1 | #REF! | M | #REF!
Site Performance Improvements, Q2 | #REF! | M | #REF!
KR Virtual Account Bank Transfer Adyen-Inicis | #REF! | #REF! | #REF!
Mobile Site Global Rollout, Wave 4 | #REF! | #REF! | #REF!
Banner Optimization | #REF! | #REF! | #REF!
SEO Url Optimization | #REF! | #REF! | #REF!
Demandware Transactional Email Redesign | #REF! | #REF! | #REF!
Product Sets | #REF! | #REF! | #REF!
Gift with purchase (GWP) | #REF! | #REF! | #REF!
Translation Tools | #REF! | #REF! | #REF!
Social Sign-In Enhancements | #REF! | #REF! | #REF!
Mobile Only Couponing | #REF! | #REF! | #REF!
Storefront Toolkit | #REF! | #REF! | #REF!
CDN Optimization | #REF! | #REF! | #REF!
Global PDP Enhancements, Phase 1 | #REF! | #REF! | #REF!
Adyen APAC, Phase 2 | #REF! | #REF! | #REF!
Merchandising Automation, Phase 2 | #REF! | #REF! | #REF!
Expanding Wish List Feature | #REF! | #REF! | #REF!
TW/SG COD | #REF! | #REF! | #REF!
Get US BazaarVoice Reviews into AU, SG | #REF! | #REF! | #REF!
APAC PDP Template | #REF! | #REF! | #REF!
Dynamic Size Chips | #REF! | #REF! | #REF!
Store Locator | #REF! | #REF! | #REF!
Size Chart Rollout | #REF! | #REF! | #REF!
Landing Page Templates | #REF! | L | #REF!
Jira Implementation | #REF! | #REF! | #REF!
ARC eCom, Phase 2 | #REF! | M | #REF!
Monetate Integration | Q1 | S | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-198 (hidden)
Project | Q? | Size | Points
Cart Improvements, Phase 1 | Q1 | M | #REF!
Merchandising Automation, Phase 1 | Q1 | S | #REF!
US ebay upgrades | Q1 | M | #REF!
Adyen Rollout for AU | Q1 | M | #REF!
| #REF! | #REF! | #REF! | = Adjusted from original prioritization
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-202 (hidden)
Project | Q? | Size | Points | For Retrospective PPT
Cart Improvements, Phase 2: Cart Level Upsell | #REF! | #REF! | #REF! | #REF! | #REF! | Total Points
Cart Improvements, Phase 3: Promotional Nearness Messaging | #REF! | #REF! | #REF! | #REF!
Improved newsletter registration workflow APAC | #REF! | #REF! | #REF! | #REF!
Redesign: JP | #REF! | #REF! | #REF! | #REF!
Redesign: KR | #REF! | #REF! | #REF! | #REF!
SAP Card Connect Integration | #REF! | #REF! | #REF! | #REF!
LinkShare US (8605) | #REF! | #REF! | #REF! | #REF!
KR Virtual Account Bank Transfer Adyen-Inicis | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-204 (hidden)
Project | Q? | Size | Points | For Retrospective PPT
APAC PDP Template | #REF! | #REF! | #REF! | #REF! | #REF! | Total Points
Checkout Redesign US | #REF! | #REF! | #REF! | #REF!
JP/KR Cart Upgrades | #REF! | M | #REF! | #REF!
Merchandising Automation, Phase 2 | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-206 (hidden)
Project | Q? | Size | Points | For Retrospective PPT
APAC PDP Template | #REF! | #REF! | #REF! | #REF! | #REF! | Total Points
Checkout Redesign US | #REF! | #REF! | #REF! | #REF!
JP/KR Cart Upgrades | #REF! | M | #REF! | #REF!
Merchandising Automation, Phase 2 | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-208 (hidden)
Project | Q? | Size | Points | For Retrospective PPT
Demandware Transactional Email Redesign | #REF! | #REF! | #REF! | #REF! | #REF! | Total Points
Global PDP Enhancements, Phase 1 | #REF! | #REF! | #REF! | #REF!
Landing Page Templates | #REF! | #REF! | #REF! | #REF!
SAP Card Connect Integration (part 2) | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-q3-q3plan (hidden)
Project | Q? | Size | Points | For Retrospective PPT
APAC PDP Template | #REF! | #REF! | #REF! | #REF! | #REF! | Total Points
Checkout Redesign International | #REF! | #REF! | #REF! | #REF!
Checkout Redesign US | #REF! | #REF! | #REF! | #REF!
JP/KR Cart Upgrades | #REF! | S | #REF! | #REF!
Merchandising Automation, Phase 2 | #REF! | #REF! | #REF! | #REF!
SAP Card Connect Integration (part 2) | #REF! | M | #REF! | #REF!
Card Connect , 1-Step Refactor | #REF! | M | #REF! | #REF!
PayPal AU | #REF! | #REF! | #REF! | #REF!
PayPal SG | #REF! | #REF! | #REF! | #REF!
Translation Tools | #REF! | #REF! | #REF! | #REF!
Social Sign-In Enhancements | #REF! | #REF! | #REF! | #REF!
Storefront Toolkit | #REF! | #REF! | #REF! | #REF!
Global PDP Enhancements, Phase 1 | #REF! | #REF! | #REF! | #REF!
Adyen TW | #REF! | #REF! | #REF! | #REF!
Landing Page Templates | #REF! | L | #REF! | #REF!
Store Locator | #REF! | L | #REF! | #REF!
Demandware Transactional Email Redesign | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## velocity-q4-q3plan (hidden)
Project | Q? | Size | Points | For Retrospective PPT
Site Preference Management | #REF! | M | #REF! | #REF! | #REF! | Total Points
CDN Optimization | #REF! | #REF! | #REF! | #REF!
Upgrade Global/Regional eCom CPCs for current business objectives | #REF! | M | #REF! | #REF!
Get US BazaarVoice Reviews into AU, SG | #REF! | #REF! | #REF! | #REF!
Size Chart Rollout | #REF! | M | #REF! | #REF!
Jira Implementation | #REF! | #REF! | #REF! | #REF!
ARC eCom, Phase 2 | #REF! | M | #REF! | #REF!
Localize Merchandise Automation Reports | #REF! | #REF! | #REF! | #REF!
Localize Shoefinder | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!
| #REF! | #REF! | #REF!

## m3-stage (hidden)
COSTS
Project | Dis/Def, Pl | Dis/Def, Act | Dev, Pl | Dev, Act | Dep, Pl | Dep, Act
XYZCompany club digital interface and data routing | 7980 | 9566 | 5040 | 12786 | 7910 | 2636
Mobile Site Global Rollout | 17920 | 5250 | 21168 | 700 | 20944 | 10290
Redesign: JP/KR/BR Discovery | 11250 | $13,350
Redesign: BR | 12544 |  | 12544 |  | 6272
Redesign: JP | 12544 |  | 12544 |  | 6272
Redesign: KR | 12544 |  | 12544 |  | 6272
Site Performance Optimization | 29988 | 12600 | 29988 | 20000 | 14994 | 2050

## release_2013 (hidden)
Release | Original Date | Actual Date | Reason for slip | Notes
146 | 2013-01-16 | 2013-01-17
149 | 2013-01-31
151 | 2013-02-14
154 | 2013-03-07
157 | 2013-04-02
160 | 2013-04-22
162 | 2013-05-01
164 | 2013-05-21
166 | 2013-05-30
168 | 2013-06-18
171 | 2013-07-10
172 | 2013-07-25
176 | 2013-08-21
179 | 2013-08-29
182 | 2013-09-19
186 | 2013-10-21
190 | 2013-11-13

## m3-req-trace (hidden)
Project | Req # | Type | Requirement Name | Comp? | Proj+Type+Comp | PROJECT | Pl | Ac | Dif
PayPal | 1 | pln | Order Placement Express Checkout (PayPal Only) | y | PayPalplny | PayPal | 11 | 11 | 0
PayPal | 2 | pln | Order Placement Standard Checkout (PayPal only) | y | PayPalplny | XYZCompany club digital interface and data routing | 11 | 10 | -1
PayPal | 3 | pln | Order Placement Standard Checkout (PayPal and Gift Card) | y | PayPalplny | Redesign: JP | 36 | 36 | 0
PayPal | 4 | pln | Cancelled order (PayPal Only) | y | PayPalplny | Redesign: BR | 29 | 0 | -29
PayPal | 5 | pln | Order Placement with cut lines (PayPal Only) | y | PayPalplny | Redesign: KR | 29 | 29 | 0
PayPal | 6 | pln | Order Placement with cut lines resulting in negative balance in E1 (PayPal and Gift Card) (This process is the same as Credit and Gift that is currently in place, but PayPal is used in place of the Credit Card.) | y | PayPalplny | Mobile Site Global Rollout | 9 | 9 | 0
PayPal | 7 | pln | Order Placement with failed Authorization (PayPal Only or Dual Payment) | y | PayPalplny | Cart Updates, Phase I | 6 | 0 | -6
PayPal | 8 | pln | Return/RMA is placed (PayPal only order) | y | PayPalplny | Cart Updates, Phase II | 9 | 0 | -9
PayPal | 9 | pln | Return/RMA is placed (PayPal and Gift Card)(Same process as Credit and Gift) | y | PayPalplny | Cart Updates, Phase III | 5 | 0 | -5
PayPal | 10 | pln | Session timeout after PayPal payment is requested | y | PayPalplny
PayPal | 11 | pln | Order Placement Express Checkout minicart (PayPal Only) | n | PayPalplnn
PayPal | 12 | add | Diable PayPal for retail endless aisle iPads | y | PayPaladdy
XYZCompany club digital interface and data routing | 1 | pln | Activate XYZCompany Club membership by collecting and storing additional customer-entered data via a web form | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 2 | pln | Allow Site Manager to enable or disable collection of XYZCompany Club data | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 3 | pln | Collect different sets of XYZCompany Club data by Locale (e.g., en_US) | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 4 | pln | Support multiple input types for XYZCompany Club profile questions | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 5 | pln | Allow site managers to exclude XYZCompany Club landing pages or sign-up pages from organic search crawlers | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 6 | pln | Display a variety of text and image messages that reference the XYZCompany Club signup process | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 7 | pln | Display a variety of calls to action that trigger the XYZCompany Club signup process | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 8 | pln | Append new form XYZCompany Club (My-Account-Club) to new account Registration flow | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 9 | pln | Pass Club data to ExactTarget | y | XYZCompany club digital interface and data routingplny
XYZCompany club digital interface and data routing | 10 | pln | Pass Club data to Epicor CRM | n | XYZCompany club digital interface and data routingplnn
XYZCompany club digital interface and data routing | 11 | pln | Track Club engagement through Omniture | y | XYZCompany club digital interface and data routingplny
Mobile Site Global Rollout | 1 | pln | Smarphone UK, DE, AU, CA: Search | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 2 | pln | Smarphone UK, DE, AU, CA: Browse | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 3 | pln | Smarphone UK, DE, AU, CA: Buy Workflow | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 4 | pln | Tablet Level 1 Optimization UK, DE, AU, CA: Search | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 5 | pln | Tablet Level 1 Optimization UK, DE, AU, CA: Browse | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 6 | pln | Tablet Level 1 Optimization UK, DE, AU, CA: Buy Workflow | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 7 | pln | Smarphone UK, DE, AU, CA: Account | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 8 | pln | Smarphone UK, DE, AU, CA: Buy Customer Service | y | Mobile Site Global Rolloutplny
Mobile Site Global Rollout | 9 | pln | Smarphone UK, DE, AU, CA: Store Locator | y | Mobile Site Global Rolloutplny
Redesign: JP | 1 | pln | Add Global Promo bar to Japan site. | y | Redesign: JPplny
Redesign: JP | 2 | pln | Global Masthead for Japan | y | Redesign: JPplny
Redesign: JP | 3 | pln | Mini cart hover needs to be added to Japan site | y | Redesign: JPplny
Redesign: JP | 4 | pln | Add Certona to Japan site. | y | Redesign: JPplny
Redesign: JP | 5 | pln | Update the Japan site to include the MegaMenu. | y | Redesign: JPplny
Redesign: JP | 6 | pln | Update Hero Carousel on Japan site | y | Redesign: JPplny
Redesign: JP | 7 | pln | Update featured content on Japan’s home page | y | Redesign: JPplny
Redesign: JP | 8 | pln | Remove secondary nav in the Japan site | y | Redesign: JPplny
Redesign: JP | 9 | pln | Update Footer | y | Redesign: JPplny
Redesign: JP | 10 | pln | Include the Just for You section for Japan site. | y | Redesign: JPplny
Redesign: JP | 11 | pln | Global gender landing page needs to be added to Japan site. | y | Redesign: JPplny
Redesign: JP | 12 | pln | Update Category page | y | Redesign: JPplny
Redesign: JP | 13 | pln | Update Sub-Category page | y | Redesign: JPplny
Redesign: JP | 14 | pln | Update Product Page (page 2 of a category/subcategory page) | y | Redesign: JPplny
Redesign: JP | 15 | pln | Quick Overlay functionality | y | Redesign: JPplny
Redesign: JP | 16 | pln | Update PDP page on Japan site | y | Redesign: JPplny
Redesign: JP | 17 | pln | Update Cart section on Japan site | y | Redesign: JPplny
Redesign: JP | 18 | pln | Update Checkout | y | Redesign: JPplny
Redesign: JP | 19 | pln | Adyen | y | Redesign: JPplny
Redesign: JP | 20 | pln | Search needs to be updated to match the new layout | y | Redesign: JPplny
Redesign: JP | 21 | pln | Addition of the customer service page on the Japan site | y | Redesign: JPplny
Redesign: JP | 22 | pln | The fit and size guide will require some formatting updates | y | Redesign: JPplny
Redesign: JP | 23 | pln | My Account page | y | Redesign: JPplny
Redesign: JP | 24 | pln | Order Status Update | y | Redesign: JPplny
Redesign: JP | 25 | pln | Store Locator | y | Redesign: JPplny
Redesign: JP | 26 | pln | Review details to be updated | y | Redesign: JPplny
Redesign: JP | 27 | pln | Email subscriptions for Japan | y | Redesign: JPplny
Redesign: JP | 28 | pln | Gift Wrapping | y | Redesign: JPplny
Redesign: JP | 29 | pln | Returns | y | Redesign: JPplny
Redesign: JP | 30 | pln | Bazaarvoice to be updated (hosted version) | y | Redesign: JPplny
Redesign: JP | 31 | pln | LinkShare | y | Redesign: JPplny
Redesign: JP | 32 | pln | Criteo | y | Redesign: JPplny
Redesign: JP | 33 | pln | Google | y | Redesign: JPplny
Redesign: JP | 34 | pln | Yahoo | y | Redesign: JPplny
Redesign: JP | 35 | pln | Adcom | y | Redesign: JPplny
Redesign: JP | 36 | pln | Cosmi | y | Redesign: JPplny
Redesign: KR | 1 | pln | Add Global Promo bar to Korea site. | y | Redesign: KRplny
Redesign: KR | 2 | pln | Global Masthead for Korea | y | Redesign: KRplny
Redesign: KR | 3 | pln | Mini cart hover needs to be added to Korea site | y | Redesign: KRplny
Redesign: KR | 4 | pln | Add Certona to Korea site. | y | Redesign: KRplny
Redesign: KR | 5 | pln | Update the Korea site to include the MegaMenu. | y | Redesign: KRplny
Redesign: KR | 6 | pln | Update Hero Carousel on Korea site | y | Redesign: KRplny
Redesign: KR | 7 | pln | Update featured content on Korea’s home page | y | Redesign: KRplny
Redesign: KR | 8 | pln | Remove secondary nav in the Korea site | y | Redesign: KRplny
Redesign: KR | 9 | pln | Update Footer | y | Redesign: KRplny
Redesign: KR | 10 | pln | Include the Just for You section for Korea site. | y | Redesign: KRplny
Redesign: KR | 11 | pln | Global gender landing page needs to be added to Korea site. | y | Redesign: KRplny
Redesign: KR | 12 | pln | Update Category page | y | Redesign: KRplny
Redesign: KR | 13 | pln | Update Sub-Category page | y | Redesign: KRplny
Redesign: KR | 14 | pln | Update Product Page (page 2 of a category/subcategory page) | y | Redesign: KRplny
Redesign: KR | 15 | pln | Quick Overlay functionality | y | Redesign: KRplny
Redesign: KR | 16 | pln | Update PDP page on Korea site | y | Redesign: KRplny
Redesign: KR | 17 | pln | Update Cart section on Korea site | y | Redesign: KRplny
Redesign: KR | 18 | pln | Update Checkout | y | Redesign: KRplny
Redesign: KR | 19 | pln | Adyen | y | Redesign: KRplny
Redesign: KR | 20 | pln | Search needs to be updated to match the new layout | y | Redesign: KRplny
Redesign: KR | 21 | pln | Addition of the customer service page on the Korea site | y | Redesign: KRplny
Redesign: KR | 22 | pln | The fit and size guide will require some formatting updates | y | Redesign: KRplny
Redesign: KR | 23 | pln | My Account page | y | Redesign: KRplny
Redesign: KR | 24 | pln | Order Status Update | y | Redesign: KRplny
Redesign: KR | 25 | pln | Store Locator | y | Redesign: KRplny
Redesign: KR | 26 | pln | Review details to be updated | y | Redesign: KRplny
Redesign: KR | 27 | pln | Email subscriptions for Korea | y | Redesign: KRplny
Redesign: KR | 28 | pln | Returns | y | Redesign: KRplny
Redesign: KR | 29 | pln | Bazaarvoice to be updated (hosted version) | y | Redesign: KRplny
Redesign: BR | 1 | pln | Add Global Promo bar to Brazil site. | n | Redesign: BRplnn
Redesign: BR | 2 | pln | Global Masthead for Brazil | n | Redesign: BRplnn
Redesign: BR | 3 | pln | Mini cart hover needs to be added to Brazil site | n | Redesign: BRplnn
Redesign: BR | 4 | pln | Add Certona to Brazil site. | n | Redesign: BRplnn
Redesign: BR | 5 | pln | Update the Brazil site to include the MegaMenu. | n | Redesign: BRplnn
Redesign: BR | 6 | pln | Update Hero Carousel on Brazil site | n | Redesign: BRplnn
Redesign: BR | 7 | pln | Update featured content on Brazil’s home page | n | Redesign: BRplnn
Redesign: BR | 8 | pln | Remove secondary nav in the Brazil site | n | Redesign: BRplnn
Redesign: BR | 9 | pln | Update Footer | n | Redesign: BRplnn
Redesign: BR | 10 | pln | Include the Just for You section for Brazil site. | n | Redesign: BRplnn
Redesign: BR | 11 | pln | Global gender landing page needs to be added to Brazil site. | n | Redesign: BRplnn
Redesign: BR | 12 | pln | Update Category page | n | Redesign: BRplnn
Redesign: BR | 13 | pln | Update Sub-Category page | n | Redesign: BRplnn
Redesign: BR | 14 | pln | Update Product Page (page 2 of a category/subcategory page) | n | Redesign: BRplnn
Redesign: BR | 15 | pln | Quick Overlay functionality | n | Redesign: BRplnn
Redesign: BR | 16 | pln | Update PDP page on Brazil site | n | Redesign: BRplnn
Redesign: BR | 17 | pln | Update Cart section on Brazil site | n | Redesign: BRplnn
Redesign: BR | 18 | pln | Update Checkout | n | Redesign: BRplnn
Redesign: BR | 19 | pln | Adyen | n | Redesign: BRplnn
Redesign: BR | 20 | pln | Search needs to be updated to match the new layout | n | Redesign: BRplnn
Redesign: BR | 21 | pln | Addition of the customer service page on the Brazil site | n | Redesign: BRplnn
Redesign: BR | 22 | pln | The fit and size guide will require some formatting updates | n | Redesign: BRplnn
Redesign: BR | 23 | pln | My Account page | n | Redesign: BRplnn
Redesign: BR | 24 | pln | Order Status Update | n | Redesign: BRplnn
Redesign: BR | 25 | pln | Store Locator | n | Redesign: BRplnn
Redesign: BR | 26 | pln | Review details to be updated | n | Redesign: BRplnn
Redesign: BR | 27 | pln | Email subscriptions for Brazil | n | Redesign: BRplnn
Redesign: BR | 28 | pln | Returns | n | Redesign: BRplnn
Redesign: BR | 29 | pln | Bazaarvoice to be updated (hosted version) | n | Redesign: BRplnn
Cart Updates, Phase I | 1 | pln | Full cart - add remove button | n | Cart Updates, Phase Iplnn
Cart Updates, Phase I | 2 | pln | Full cart - add contact information to header area | n | Cart Updates, Phase Iplnn
Cart Updates, Phase I | 3 | pln | Full cart - Move paypal button to left | n | Cart Updates, Phase Iplnn
Cart Updates, Phase I | 4 | pln | Full cart - Add paypal & Checkout button to top of cart | n | Cart Updates, Phase Iplnn
Cart Updates, Phase I | 5 | pln | Full cart - layout change, move shipping info to bottom | n | Cart Updates, Phase Iplnn
Cart Updates, Phase I | 6 | pln | Full cart - Analytics: Update Add to cart, Page View, Remove Product and Reduce Quantity. | n | Cart Updates, Phase Iplnn
Cart Updates, Phase II | 1 | pln | Lightbox - addition of a lightbox pop showing what has been added to cart | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 2 | pln | Lightbox - Analytics Update | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 3 | pln | Upsell - Addition of recommended products in lightbox through Certona | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 4 | pln | Upsell - provide HTML/CSS to Certona before Phase II go live | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 5 | pln | Upsell: Add new transformation in Certona, driven by backend flag to accommodate the Add to Cart button without viewing details | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 6 | pln | Upsell: Analytics Update | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 7 | pln | Lightbox: Add toggle to turn off lightbox in Demandware | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 8 | pln | Flyout: Add toggle to turn off Flyout in Demandware | n | Cart Updates, Phase IIplnn
Cart Updates, Phase II | 9 | pln | Flyout: Analytics Updates | n | Cart Updates, Phase IIplnn
Cart Updates, Phase III | 1 | pln | Promotional Nearness: Implement in Cart | n | Cart Updates, Phase IIIplnn
Cart Updates, Phase III | 2 | pln | Promotional Nearness: Implement in Flyout Minicart | n | Cart Updates, Phase IIIplnn
Cart Updates, Phase III | 3 | pln | Promotional Nearness: Implement in Lightbox Minicart | n | Cart Updates, Phase IIIplnn
Cart Updates, Phase III | 4 | pln | Promotional Nearness: Add custom field called “promotional nearness” with wild cards to specify promotional unit messaging. | n | Cart Updates, Phase IIIplnn
Cart Updates, Phase III | 5 | pln | Promotional Nearness: Anaytics Update | n | Cart Updates, Phase IIIplnn

## team structure (hidden)
Person | Abbreviated | Reports To (Innotas approval)
Corey McGinnie | CMcGinnie | PMcElroy
Aaron Juretus | AJuretus | PMcElroy
Jon Long | JLong | PMcElroy
Scott Deitz | SDeitz | PMcElroy
Nick Kuhnel | NKuhnel | PMcElroy
Peter McElroy | PMcElroy | PMcElroy
Josh Zapin | JZapin | JZapin
Keith Baltus | KBaltus | KBaltus
Brianne Calandra | BCalandra | BCalandra
Michael Crenshaw | MCrenshaw | BHemphill
William Chambers | WChambers | BHemphill
Haley Nemann | HNemann | BHemphill
Maggie Sampson | MSampson | JGeditz
Poonum Rana | PRana | JGeditz
Jodi Geditz | JGeditz | JZapin
Mark France | MFrance | BCalandra
Ben Hemphill | BHemphill | BHemphill

## resource-variables
Resource Types | Projects | hours/week
fdev | Banner Ad XYZ | 32
bdev | Site Redesign ABC
des | iPhone App 123
copy | OoO
ux
pm

## resource-model (hidden)
Redesign: BR |  |  | St. Off. | 0 | Excl | N
Diff: | 7 | #REF! | #REF! | wk #
Func. | Resource | alloc type | % Ded | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Tot Hrs | Tot Cost
pm | FLnamePM | constant | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
dw | FlnameDW | peaks | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
mw | FlnameMW | peaks | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ops | FlnameOP | builds | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ux | FLnameUX | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ba | FLnameBA | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
qa | FLnameQA | builds | 40% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Redesign: JP |  |  | St. Off. | 0 | Excl | N
Diff: | 7 | #REF! | #REF! | wk #
Func. | Resource | alloc type | % Ded | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Tot Hrs | Tot Cost
pm | FLnamePM | constant | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
dw | FlnameDW | peaks | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
mw | FlnameMW | peaks | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ops | FlnameOP | builds | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ux | FLnameUX | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ba | FLnameBA | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
qa | FLnameQA | builds | 40% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Redesign: KR |  |  | St. Off. | 0 | Excl | N
Diff: | 7 | #REF! | #REF! | wk #
Func. | Resource | alloc type | % Ded | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Tot Hrs | Tot Cost
pm | FLnamePM | constant | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
dw | FlnameDW | peaks | 25% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
mw | FlnameMW | peaks | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ops | FlnameOP | builds | 5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ux | FLnameUX | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ba | FLnameBA | tapers | 10% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
qa | FLnameQA | builds | 40% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## projectlist-codefreeze (hidden)
Japan Rollout | 1
Site Redesign Final Issues | 2
US Mobile Redesign | 2.1
mPOS Redesign | 2.2
CRM Customer Data Global | 3
Code Refactoring | 4
Skin Adyen for Redesign | 5
Online Coupon Messaging | 6 | Delayed to Q2
PayPal in AM Design | 7
Paypal in AM dev | 8 | Not scheduled
ForeSee Session Replay | 9 | Deprioritized

## allocation-codefreeze (hidden)
week of
Resource | Project | Bugs | % Allocation | 2012-11-12 | 11/19 | 11/26 | 12/3 | 12/10 | 12/17 | 12/24 | 12/31 | 1/7 | 1/14 | 1/21 | 1/28 | 2/4 | 2/11 | 2/18 | 2/25 | 3/4 | 3/11
CMcGinnie | Japan Rollout |  | 25 | bar: week of 2012-11-12 to week of 2/18
| Redesign |  | 50 | bar: week of 2012-11-12 to week of 2/18
10 | bar: week of 2012-11-12 to week of 2/18
| Bugs/Maintenance |  | 15 | bar: week of 2012-11-12 to week of 2/18
AJuretus | Bugs/Maintenance |  | 20 | bar: week of 2012-11-12 to week of 2/18
| Japan Rollout |  | 25 | bar: week of 2012-11-12 to week of 2/18
| ForeSee Session Replay |  | 20 | bar: week of 2012-11-12 to week of 2/18
| Redesign - US Mobile |  | 35 | bar: week of 2012-11-12 to week of 2/18
ZSeeling | Japan Rollout |  | 50 | bar: week of 2012-11-12 to week of 2/18
| Skin Adyen for Redesign |  | 30 | bar: week of 2012-11-12 to week of 2/18
| Code Refactoring |  | 20 | bar: week of 2012-11-12 to week of 2/18
JLong | Bugs/Maintenance |  | 40 | bar: week of 2012-11-12 to week of 2/18
| Japan Rollout - MW |  | 10 | bar: week of 2012-11-12 to week of 2/18
| CRM Phase 2 |  | 50 | bar: week of 2012-11-12 to week of 2/18
SDeitz | Bugs/Maintenance |  | 25 | bar: week of 2012-11-12 to week of 2/18
| Japan Rollout - Data loading |  | 25 | bar: week of 2012-11-12 to week of 2/18
| Ops |  | 50 | bar: week of 2012-11-12 to week of 2/18
PMcElroy | Bugs/Maintenance |  | 10 | bar: week of 2012-11-12 to week of 2/18
| Japan Rollout - dev MGT |  | 40 | bar: week of 2012-11-12 to week of 2/18
| Site Redesign - dev MGT |  | 30 | bar: week of 2012-11-12 to week of 2/18
| CRM Phase 2 - dev MGT |  | 10 | bar: week of 2012-11-12 to week of 2/18
| mPOS - Ops support |  | 10 | bar: week of 2012-11-12 to week of 2/18
Nkuhnel | Bugs/Maintenance |  | 10 | bar: week of 2012-11-12 to week of 2/18
| Mentoring |  | 20 | bar: week of 2012-11-12 to week of 2/18
| Redesign Bugs |  | 40 | bar: week of 2012-11-12 to week of 2/18
| PayPal in AM Design |  | 20 | bar: week of 2012-11-12 to week of 2/18
| mPOS Redesign |  | 10
Offshore team | Bugs/Maintenance |  | 10 | bar: week of 2012-11-12 to week of 2/18
| Japan Rollout |  | 30 | bar: week of 2012-11-12 to week of 2/4
| Regression Testing |  | 20 | bar: week of 2012-11-12 to week of 2/18
| Online Coupon Messaging |  | 10 | bar: week of 2012-11-12 to week of 2/18
| Code Refactoring |  | 20 | bar: week of 2012-11-12 to week of 2/18

## APM w Legend (hidden)
Owner: (Your Name)
Updated: (Date of Update)
# | Backlog | Impact | Effort | FOM | Date | [5 empty] | Complete | Date
1 |  |  |  | #DIV/0!
2
3
4
5
6
7
[7 empty] | Active | Hours | Who | Date
[bucket 1]
1
2
3
4
5
6
7
[bucket 2]
8
9
10
11
12
13
14
15
[6 empty] | 16 | Sustaining
17
18
19
20
21
22
23
24
25
26
27
| New Activities |  |  |  | Date
[7 empty] | Escalated |  |  | Date

## allocation_old (hidden)
week of
Resource | Project | % Allocation | 2012-06-15 | 6/22 | 6/29 | 7/6 | 7/13 | 7/20 | 7/27 | 8/3 | 8/10 | 8/17 | 8/24 | 8/31 | 9/7 | 9/14 | 9/21 | 9/28 | 10/5 | 10/12
CMcGinnie | Bugs/Maintenance | 20 | bar: week of 6/29 to week of 9/7
| Landing Page Templates | 20 | bar: week of 2012-06-15 to week of 7/6
| Site Redesign | 60 | bar: week of 2012-06-15 to week of 9/7
AJuretus | Bugs/Maintenance | 20 | bar: week of 2012-06-15 to week of 9/7
| Brazil Rollout | 20 | bar: week of 2012-06-15 to week of 8/24
| Korea Rollout | 10 | bar: week of 2012-06-15 to week of 6/22
| Japan Rollout | 50 | bar: week of 7/6 to week of 9/7
ZSeeling | Bugs/Maintenance | 10 | bar: week of 2012-06-15 to week of 9/7
| Brazil Rollout | 30 | bar: week of 6/22 to week of 8/24
| Japan Rollout | 30 | bar: week of 2012-06-15 to week of 9/7
| Adyen EU Rollout | 20 | bar: week of 6/29 to week of 7/20
| Korea Rollout | 10 | bar: week of 2012-06-15 to week of 6/22
JLong | Bugs/Maintenance | 15 | bar: week of 2012-06-15 to week of 9/7
| Brazil Rollout | 20 | bar: week of 2012-06-15 to week of 8/17
| Korea Rollout | 5 | bar: week of 2012-06-15
| Japan Rollout | 20 | bar: week of 8/24 to week of 9/7
| CRM Phase 2 | 40 | bar: week of 6/29 to week of 9/7
SDeitz | Bugs/Maintenance | 40 | bar: week of 2012-06-15 to week of 9/7
| Brazil Rollout | 40 | bar: week of 7/6 to week of 9/7
| Korea Rollout | 20 | bar: week of 2012-06-15 to week of 6/29
PMcElroy | Bugs/Maintenance | 10 | bar: week of 2012-06-15 to week of 9/7
| Brazil Rollout | 30 | bar: week of 2012-06-15 to week of 9/7
| Japan Rollout | 20 | bar: week of 2012-06-15 to week of 9/7
| Korea Rollout | 10 | bar: week of 2012-06-15 to week of 9/7
| Site Redesign | 10 | bar: week of 2012-06-15 to week of 9/7
| XYZCompany.com ES_US (MotionPoint Project) | 5 | bar: week of 2012-06-15 to week of 9/7
| CRM Phase 2 | 15 | bar: week of 2012-06-15 to week of 9/7
Offshore team | Bugs/Maintenance | 25 | bar: week of 2012-06-15 to week of 9/7
| Brazil Rollout | 35 | bar: week of 2012-06-15 to week of 9/7
| Japan Rollout | 30 | bar: week of 2012-06-15 to week of 9/7
| Korea Rollout | 5 | bar: week of 2012-06-15 to week of 7/6
| XYZCompany.com ES_US (MotionPoint Project) | 5 | bar: week of 2012-06-15 to week of 7/13

## priortization-120227 (hidden)
Projects | Region | Date Added | Date Needed | FOM | eCom Team |  | Americas |  |  |  | EU |  |  |  | APAC
[5 empty] | Effort | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Cost/Effort to Implement | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Cost/Effort to Implement | Difficulty Value | Annual Cost Savings or Revenue Generation | Impact Value | Cost/Effort to Implement | Difficulty Value
4156 - Build way to handle rejected profiles |  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Outlet Eligible problems |  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Sale pricing – unclear how long sale will run; rain checks |  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Vague dates of when a new style is coming back in stock – customers want to know |  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Store Locator |  |  |  | #N/A |  | #N/A | CS: $125K-200K/R: $187.5K-300K | 5 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
3857 - Site Specific Attribution - All XYZCompany Sites need to use site specific attributes |  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Dotomi Remarketing Purchase feed | Americas | 2012-01-18 | 2012-02-28 | 1.33 | 1 month/3 or less systems | 5 | CS: $1M+/R: $1.5M+ | 10 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Product Sets | Global | 2011-05-11 | 2011-09-30 | 1.07 | 1 month/3 or less systems | 5 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $50K-75K/E: 3 weeks | 3 | CS: $200K-300K/R: $300K-450K | 6 | C: $75K-125K/E: 4 weeks | 4 | CS: $50K-75K/R: $75K-112.5K | 6 | C: $50K-75K/E: 3 weeks | 3
Gift with purchase (GWP) | Global | 2011-09-12 | 2012-03-31 | 1.00 | 3 weeks/contained in 1 system | 4 | CS: $200K-300K/R: $300K-450K | 6 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 3 | C: $25K-50K/E: 2 weeks | 2
Couponing/Promo code redesign | Global | 2012-01-04 | 2012-06-30 | 1.00 | 1 month/3 or less systems | 5 | CS: $300K-500K/R: $450K-750K | 7 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $50K-75K/E: 3 weeks | 3
BISN Triage Phase 1 (Backend) | Global | 2011-05-18 | 2011-09-30 | 0.82 | 3 weeks/contained in 1 system | 4 | CS: $200K-300K/R: $300K-450K | 6 | C: $50K-75K/E: 3 weeks | 3 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $25K-50K/E: 2 weeks | 2
Product Feed Fixes/Improvements to optimize Comparison Shopping Engines) | Global | 2011-05-13 |  | 0.80 | 2 weeks/contained in 1 system | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $75K-125K/E: 4 weeks | 4
Email Acquisition Enhancements | Global | 2011-04-28 | 2011-06-30 | 0.75 | 2 months/3 or less systems | 7 | CS: $300K-500K/R: $450K-750K | 7 | C: $50K-75K/E: 3 weeks | 3 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Discount pricing by percentage in category and other | Global | 2011-10-24 | 2012-06-30 | 0.67 | 3 weeks/contained in 1 system | 4 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $25K-50K/E: 2 weeks | 2 | CS: $25K-50K/R: $37.5K-75K | 3 | C: $25K-50K/E: 2 weeks | 2
Catalog Sign-Up and Removal Form on Customer Service Page | Americas | 2011-11-15 | 2012-02-14 | 0.63 | 1 month/3 or less systems | 5 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week | 1 | CS: $25K-50K/R: $37.5K-75K | 2 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Pre-Orders | Global | 2011-11-21 | 2012-06-30 | 0.53 | 3 months+/4 + | 10 | CS: $75K-125K/R: $112.5K-187.5K | 4 | C: $25K-50K/E: 2 weeks | 2 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Seamless SMS-Opt-in Process Online | Americas | 2011-10-14 | 2012-03-30 | 0.38 | 1 month/3 or less systems | 5 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Recommendation engine | Global | 2012-01-10 | 2012-06-30 | #N/A |  | #N/A | CS: $750K-1M/R: $1.125M-1.5M | 9 | C: $50K-75K/E: 3 weeks | 3 | CS: $125K-200K/R: $187.5K-300K | 5 | C: $0-25K/E: 1 week | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $0-25K/E: 1 week | 1
Cart Optimization | Global | 2012-01-04 | 2012-03-30 | #N/A |  | #N/A | CS: $1M+/R: $1.5M+ | 10 | C: $25K-50K/E: 2 weeks | 2 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $50K-75K/R: $75K-112.5K | 3 | C: $50K-75K/E: 3 weeks | 3
Gift Card Bug Fix | Global | 2012-01-15 | 2012-05-01 | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Google Trusted Store* |  |  |  | #N/A |  | #N/A | CS: $1M+/R: $1.5M+ | 10 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
Trendyr, APAC* |  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1
|  |  |  | #N/A |  | #N/A | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1 | CS: $0-25K/R: $0-37.5K | 1 | C: $0-25K/E: 1 week | 1

## legend (hidden)
Region | Detail | Phase | Detail | Type | Detail
AM | Americas | DIS | Discovery | DWC | DemandWare CAPEX
AP | APAC | DEF | Define | DWM | DemandWare Maintenance
EU | EU | DES | Design | MWC | MiddleWare CAPEX
GL | Global | DEV | development | MWM | MiddleWare Maintenance
|  | DEP | Deploy | DPC | Digital Production CAPEX
|  |  |  | DPM | Digital Production Maintenance
|  |  |  | MKT | Marketing Production Budget
|  |  |  | OTH | Other

## fom-pulldowns (hidden)
Grade | Definition | Abb. | Value
Must | MUST have this. | M | 5
Should | SHOULD have this if at all possible. | S | 3
Could | COULD have this if it does not effect anything else. | C | 2
Would | WOULD be nice to have but some time in the future. | W | 1
FOM - Effort
Effort | Systems Impacted | Effort/Systems Impacted | Value
1 week | only config change in 1 system | 1 week/only config change in 1 system | 1 | 1=1 week/only config change in 1 system
1 week | contained in 1 system | 1 week/contained in 1 system | 2 | 2=1 week/contained in 1 system
2 weeks | contained in 1 system | 2 weeks/contained in 1 system | 3 | 3=2 weeks/contained in 1 system
3 weeks | contained in 1 system | 3 weeks/contained in 1 system | 4 | 4=3 weeks/contained in 1 system
1 month | 3 or less systems | 1 month/3 or less systems | 5 | 5=1 month/3 or less systems
1 month | 4 + | 1 month/4 + | 6 | 6=1 month/4 +
2 months | 3 or less systems | 2 months/3 or less systems | 7 | 7=2 months/3 or less systems
2 months | 4 + | 2 months/4 + | 8 | 8=2 months/4 +
3 months | 3 or less systems | 3 months/3 or less systems | 9 | 9=3 months/3 or less systems
3 months+ | 4 + | 3 months+/4 + | 10 | 10=3 months+/4 +
FOM - Impact - Region
Cost Savings | Revenue | CS/R | Value
$0-25K | $0-37.5K | CS: $0-25K/R: $0-37.5K | 1
$25K-50K | $37.5K-75K | CS: $25K-50K/R: $37.5K-75K | 2
$50K-75K | $75K-112.5K | CS: $50K-75K/R: $75K-112.5K | 3
$75K-125K | $112.5K-187.5K | CS: $75K-125K/R: $112.5K-187.5K | 4
$125K-200K | $187.5K-300K | CS: $125K-200K/R: $187.5K-300K | 5
$200K-300K | $300K-450K | CS: $200K-300K/R: $300K-450K | 6
$300K-500K | $450K-750K | CS: $300K-500K/R: $450K-750K | 7
$500K-750K | $750K-1.125M | CS: $500K-750K/R: $750K-1.125M | 8
$750K-1M | $1.125M-1.5M | CS: $750K-1M/R: $1.125M-1.5M | 9
$1M+ | $1.5M+ | CS: $1M+/R: $1.5M+ | 10
FOM - Effort/Cost - Region
Cost to Implement | Effort to Implement | CS/E | Value
$0-25K | 1 week | C: $0-25K/E: 1 week | 1
$25K-50K | 2 weeks | C: $25K-50K/E: 2 weeks | 2
$50K-75K | 3 weeks | C: $50K-75K/E: 3 weeks | 3
$75K-125K | 4 weeks | C: $75K-125K/E: 4 weeks | 4
$125K-200K | 5 weeks | C: $125K-200K/E: 5 weeks | 5
$200K-300K | 6 weeks | C: $200K-300K/E: 6 weeks | 6
$300K-500K | 7 weeks | C: $300K-500K/E: 7 weeks | 7
$500K-750K | 8 weeks | C: $500K-750K/E: 8 weeks | 8
$750K-1M | 9 weeks | C: $750K-1M/E: 9 weeks | 9
$1M+ | 10+ weeks | C: $1M+/E: 10+ weeks | 10